## F&A Q1 Performance
Q1 PERFORMANCE REPORTING FOR VOTE FUNCTION: POLICY, PLANNING AND SUPPORT SERVICES
|  | Q1 PLANNED ACTIVITIES FOR FINANCE AND ADMINISTARTION |  |  | ACTUAL PERFORMANCE
SERVICE AREA/PIAP OUTPUT | Annual Output | Planned Q1 Target | Approved budget | Warrant/payments | Achieved Q1 physical performance | Amount Spent | Reasons for Variation
Key Service Area: 000001 Audit and Risk Management; PIAP Output 10511605 Audit and Risk Management undertaken (Responsibility center-Principal Internal Auditor) | Domestic Arrears prepared, reviewed and submitted to Office of Auditor General | Domestic Arrears prepared, reviewed and submitted to Office of Auditor General |  |  | The Domestic Arrears report prepared and submitted to Office of the Internal Auditor General |  | Target Achieved
| Annual Payroll (salary and pension) audit reviews undertaken | Quarterly Payroll (salary and pension) audit reviews undertaken |  |  | Annual payroll (active and Pension ) reviewed and report produced |  | Target Achieved
| Quarterly audits undertaken in 22 ministry Zonal offices produced | Quarterly internal audits undertaken in 22 ministry Zonal offices produced |  |  | Quarterly internal audits undertaken in 4 MZOs and a report prepared including; Kyadondo, Busiro, Mpigi and Bukalasa |  | Target Achieved
| Training of Trainers for all HoDs and all MZO heads on Good Audit Practices undertaken. | HODs and MZO heads trained in good audit practices |  |  | Activity Not undertaken |  | Target Not Achieved
| Capacity of Audit staff enhanced in Audit Management, risk other audit competencies | Capacity of Audit staff enhanced in Audit Management, risk other audit competencies |  |  | One (01) staff trained in advanced risk management |  | Target Achieved
| Draft Financial Statements for FY2025/26 prepared | End of FY2025/26 Draft Financial Statement Audit report produced |  |  | Financial statements reviewed and report produced |  | Target Achieved
| Internal audit reports produced | Quarterly internal audit reports produced |  |  | 1st quarter internal audit report produced |  | Target Achieved
| Quarterly Audit Committee Meetings held | 1 Audit Committee Meeting held |  |  | One (01) audit committee meeting held in September 2026 |  | Target Achieved
Annual Budget |  | Quarter one budget | 97500 |  |  | 97500
Key Service Area: 000004 Finance and Accounting; PIAP Output 10511602 Final accounts prepared ( Head Accounts) | UGX 5.8Bn NTR collected and accounted for | 1.45 bn NTR collected and accounted for |  |  | NTR worth UGX 2,343,151,730 bn collected and accounted for. | Budget Nuetral | Target Achieved
| IFMS and IPPS systems maintained | IFMS and IPPS systems maintained |  |  | IFMS and IPPS systems maintained | 55400000 | Target Achieved
| Responses and reports provided onFinancial audit issues | Responses and reports provided onFinancial audit issues |  |  | Responses on Financial audit issues for FY 2025/26 prepared and submitted to Accountant General's office. | 67265000 | Target Achieved
| Quarterly warrants prepared and submited | Quarterly warrants prepared and submited |  |  | Quarterly (Q1) FY 2026/27 warrants prepared and submited To the Accountant General. | 22500000 | Target Achieved
Annual Budget | 600000 | Quarter one budget | 150000 |  |  | 145165000
Key Service Area: 000005 Human Resource Management; PIAP Output 10511609 Human Resource Management undertaken ( AC/HR) | Payroll verified and updated quarterly | Payroll verified and updated quarterly | 5960000 |  | 100% | 5960000 | Target Achieved
| 1 trainings on Human Capital Management (HCM) training on self-service modules and mindset undertaken for staff | 1 trainings on Human CapitalManagement (HCM) training on self service modules and mindset undertaken for staff |  |  | 01 training on Human Capital Management (HCM) training on self-service modules |  | Target Achieved
| Ministry Capacity Building Plan developed | Ministry Capacity Building Plan developed |  |  | Ministry Capacity Building Plan development is ongoing data being compiled/collected |  | Target Achieved
| Human Resource performance Monitored and supervised in 22 MZOs | Human Resource performance Monitored and supervised in 22 MZOs |  |  | Human Resource performance Monitored and supervised in forteen (14) MZOs e.g. Mbale, Jinja, Mukono, Soroti, |  | Target Achieved
| Quarterly Pensioner's Validation exercises undertaken | Quarterly Pensioner's Validation exercises undertaken |  |  | Pensioners payments and verifications undertaken |  | Target Achieved
| Weekly Wellness and fitness training provided for all ministry staff | Weekly Wellness and fitness training provided for all ministry staff |  |  | Weekly Wellness and fitness training provided for all ministry staff |  | Target Achieved
| Annual General staff meeting held | N/A |  |  | Annual General staff meeting held on 14/08/2026. |  | Target Achieved
| Quarterly Training committee meetings held | Quarterly Training committee meetings held |  |  | Quarterly Training committee meetings held date |  | Target Achieved
| Membership dues to Uganda Human Resource Managers Association and Africa Public Sector Human Resource Network paid | N/A |  |  | Membership dues to Uganda Human Resource Managers Association and Africa Public Sector Human Resource Network paid |  | Target Achieved
| HCM System maintained | HCM system maintained |  |  | HCM system maintained |  | Target Achieved
Annual Budget |  | Quarter one budget | 3029447 |  |  | 3029447
Key Service Area: 000007 Procurement and Disposal Services; PIAP Output 10511608 Procurement management ( Head Procurement) | Annual Department Procurement plans validated and approved | Annual Department Procurement plans validated and approved |  |  | The Annual departmental procurement plans were consolidated and approved by the Accounting Officer. |  | Target Achieved
| 12 Departments and contracts Committee trained on EGP-12 | 12 Departments and contracts Committee trained on EGP-12 |  |  | Not undertaken |  | Inadequate funds
| 1020 Contracts for works, goods, and services prepared | 255 Contracts for works, goods and services prepared |  |  | Prepared One hundred twenty (120) contracts for works, goods and services. |  | Target Partially Achieved
| Refresher trainings for 4 procurement staff undertaken | N/A | N/A | N/A | N/A | N/A | N/A
| 12 PPDA and Financial compliance report prepared and submitted | 12 PPDA and Financial compliance report prepared and submitted |  |  | Three (03) PPDA and Financial compliance report prepared and submitted |  | Target Achieved
| All contracts both GoU and development projects monitored quarterly | All contracts both GoU and development projects monitored quarterly
| 12 Contracts Committee meetings held | 3 Contracts Committee meetings held |  |  | Four (04) contracts committee meetings held. |  | Target Achieved
| 4 procurement performance reports prepared | Q1 procurement report prepared |  |  | Q1 procurement report prepared |  | Target Achieved
Annual Budget |  | Quarter one budget | 87500
Key Service Area: 000008 Records Management; PIAP Output 10511610 Efficient Records management (Senior Records Officer) | 4000 Personnel and subject files scanned and uploaded to the system | 500 Personnel and subject files scanned and uploaded on the system |  |  | Subject files have all been scanned and uploaded on the EDRMS | 16000000 | Target Achieved
| Ministry registry on-boarded on electronic Document and records management system | Ministry registry on-boarded on electronic Document and records management system |  |  | The Ministry on boarded on electronic Document Management System | 10000000 | Target Achieved
| Staff capacity built on navigation of EDRMS | Staff capacity built on navigation of EDRMS |  |  | A total of 150 staff trained, including Senior Management, Principal Officers, Senior Officers at Headquarters and IT staff. | 12400000 | Target Achieved
| Refresher Training undertaken for 4 registry staff in Proper Records Management practices | Refresher Training undertaken for 2 registry staff in Proper Records Management practices |  |  | 2 Records staff where taken through EDRMS and they formed part of the team of Trainings of Trainers for EDRMS. | 3000000 | Target Achieved
| 5000 Backlog files scanned and uploaded into the electronic document management system (EDRMS) | 700 Backlog files scanned and uploaded into the electronic document management system (EDRMS) |  |  | 350 Backlog files scanned and the uploaded into the system. | 9400000 | Target partially Achieved, will be expedited in Q2
| 300 Semi current records appraised | N/A |  |  | N/A | N/A | N/A
| Records Management supervised in the 22 Ministry Zonal Offices | Records Management supervised in the 5 Ministry Zonal Offices |  |  | Regisyties supervised and these include; Arua, Gulu, Lira, Moroto, Soroti | 20400000 | Target Achieved
| File census conducted both at Headquarters and Ministry Zonal Offices | N/A | N/A | N/A | N/A | N/A | N/A
Annual Budget | 400000 | Quarter one budget | 87050 |  |  | 71200000
Key Service Area: 000010 Leadership and Management; PIAP Output 10511607 Leadership and Management coordinated ( PAS) | 12 Top/Policy Management meetings held | 03 Top/Policy Management meetings held |  |  | 02 Top/Policy Management meetings held |  | Target Achieved
| 08 political oversight exercise undertaken and Reports produced | 02 political oversight exercises undertaken and Reports produced |  |  | 02 political oversight exercises undertaken and Reports produced |  | Target Achieved
| 12 Senior Management meetings held | 03 Senior Management meetings held |  |  | 03 Senior Management meetings held |  | Target Achieved
| 04 International Obligations and conferences attended | 1 International Obligations and conferences attended |  |  | 01 International Obligation and conference attended |  | Target Achieved
| Responses to Cabinet issues prepared | Responses to Cabinet issues prepared |  |  | Responses to Cabinet issues prepared |  | Target Achieved
Annual Budget | 525600 | Quarter one budget | 525600 |  |  | 525600
Key Service Area: 000011 Communication and Public Relations;PIAP Output 10511606 Communication and Public Relations strengthened ( Senior Information Officer) | 08 Barazas/open days organized to sensitize the public on Ministry services, profile complaints, responses, and grievances in 2 Districts in the Eastern Region, i.e Tororo and Mbale | 2 Barazas/open days organized to sensitize the public on Ministry services,profile complaints, responses andgrievances in 2 Districts in Eastern Region i.e Tororo and Mbale |  |  | 4 Barazas Held. Mbarara, Luweero, Masindi, Jinja and and complaints handling sensitization on the procedures for land transactions in Tororo. We also established the number of SLAAC Titles ISSUEd Carried out sensitization for land owners in 13 sub-counties under Buwamba county in Bundibudyo. | 45200000 | We held Open 4 Open Days. Tororo MZO had already organized their open day. We simply facilitated it.
| Ministry website Upgraded and mantained | Ministry website Upgraded and mantained |  |  | Ministry website updated and maintained. Guidelines on Special Titles, Circular NO.1 of 2026 on Management of land disputes uploaded, Revised Ministry Communication strategy, UCMID Job Application Documents, Blogs on Nationwide Stakeholder engagements on development of Land Inventory, lists of special titles July – August
| 6,000 information requests responded to from both men and women | 1,500 information requests from both men and women responded to from both men and women |  |  | 757 information requests were responded to against 1500. 67.19% were men and 34.12% were women. | N/A | There was two months when the call center had broken down.
| Communications equipment; cameras, ICT mantained and serviced | Communications equipment; cameras, ICT mantained and serviced |  |  | Equipment wasn’t maintained and serviced this quarter but will be handled in quarter 2. | 0
| Subscription for Tidio andTwitter Blue paid | Subscription for Tidio andTwitter Blue paid |  |  | Subscriptions weren’t purchased. We will resubmit the subscriptions the next quarter. | 0 | Requisition was made but approval wasn’t done.
| Ministry IEC material i.e access to information manual, client charter land procedures developed, printed disseminated | Ministry IEC material i.e access to information manual, client charter land procedures developed, printed disseminated |  |  | Developed the client charter and land procedures and access to information manual. 5 Posters on procedures and 1 poster on access to information and 1 poster on client’s charter. Developed materials in partnership with office of the Prime Minister for the Yumbe - Obongi border demarcation. Developed a documentary the benefits of the registration of land in Parish to Market Model.
| Competencies of 4 Communications Division staff strengthened in public relations, crisis communication, and dissemination | N/A |  |  | Next Quarter activity. |  | This is a Q2 activity. There was no budget for this activity in Q1.
| Targetted ministry advets and communications designed and placed | Targeted ministry Adverts and communications designed and placed |  |  | Developed guidelines for Busuulu in both English and Luganda. 500 copies for English and 500 copies for Luganda and 500 copies for the usage of UgNLIC app. Gazettes designed and shared. Translated land awareness materials into Luganda and Rukonjo for Rwenzori Land Awareness Week. |  | Achieved.
| Ministry IEC material translated to Luganda, and Ateso and disseminated during the open days | Ministry IEC material translated to Luganda, and Ateso and disseminated during the open days |  |  | We developed the Tegera Essonga ze Ettaka mu Uganda. A Luganda book with land procedures. We issued the booklets during the open day engagements in Nabbingo and in Rwenzori Sub-region during the land awareness week.
Annual Budget | 400000 | Quarter one budget | 98000
Key Service Area: 000013 HIV/AIDS Mainstreaming;PIAP Output 10511604 Cross cutting issues mainstreamed ( TBD) | 04 HIV/AIDs/Malaria/Tuberclosis committee meetings held | 01 HIV/AIDs/Malaria/Tuberculosis Committee meeting held |  |  | 01 HIV/AIDs/Malaria/Tuberculosis Committee meeting held |  | Target Achieved
| Condoms procured quarterly for all 26 staff structures (22 Ministry Zonal Offices, Head quarters and the National Land Information | condoms procured and maintained for all 26 staff structures |  |  | Condoms procured and maintained for all 26 staff structures |  | Target Achieved
| 02 Voluntary Counselling and Testing exercises undertaken for staff | N/A |  |  | Counselling and Testing exercises undertaken for staff |  | Target Achieved
| Condom dispensers procured and placed in all washrooms at both Headquarters and Ministry Zonal Offices | Condom dispensers procured and placed in all washrooms at both Ministry and Zonal offices |  |  | Condom dispensers procured and placed in all washrooms at both Ministry and Zonal offices |  | Target Achieved
| Quarterly HIV /AIDS, Malaria, and Tuberculosis sensitisation exercise undertaken | Q1 HIV /AIDS, Malaria and Tuberculosis sensitisation exercise undertaken |  |  | HIV /AIDS, Malaria, and Tuberculosis sensitization exercise undertaken. |  | Target Achieved
Annual Budget | 100000 | Quarter one budget | 20000
Key Service Area: 000014 Administrative and Support Services; PIAP Output 10511101 Enhanced coordination and programme secretariat services ( AC/Planning) | 12 months Guard and security services provided for the Ministry headquarters and the National Land Information Center | 3 months Guard and security services provided for the Ministry headquarters and the national land Information Center |  |  | 3 months Guard and security services provided for the Ministry headquarters and the national land Information Center |  | Target Achieved
| 50 transport equipment installed with new security-enhanced Digital Number Plates | 10 transport equipment installed with |  |  | 10 transport equipment installed with new security-enhanced Digital Number Plates |  | Target Achieved
| Annual utility bills paid | Quarter 1 utility bills paid |  |  | Quarter 1 utility bills paid |  | Target Achieved
| Minor repairs on civil works undertaken | Minor repairs on civil works undertaken in quarter 1 |  |  | Minor repairs on civil works undertaken in quarter 1 |  | Target Achieved
| All Ministry fleet maintained and serviced regularly | All Ministry fleet maintained and serviced regularly |  |  | All Ministry fleet maintained and serviced regularly |  | Target Achieved
| Property management/cleaning services provided for all Ministry offices | Property management/cleaning services provided for all Ministry offices |  |  | Property management/cleaning services provided for all Ministry offices |  | Target Achieved
| Annual Ministry property rates paid | Quarter 1 Ministry property rates paid |  |  | Quarter 1 Ministry property rates paid |  | Target Achieved
| Computer software and Anti viruses procured | N/A |  |  | N/A |  | N/A
| 171 MVs serviced and maintained | 171 MVs serviced and maintained |  |  | 171 MVs serviced and maintained |  | Target Achieved
| UGX 25bn paid as compesation to ranchers and third parties | Compensation paid to ranchers and third parties |  |  | Compensation paid to ranchers and third parties |  | Target Achieved
Annual Budget | 29250000 | Quarter one budget | 1055000 |  |  | 1055000
Key Service Area: 000006 Planning and Budgeting services; PIAP Output 10511601 Planning and Budgeting Services undertaken | Draft budget Estimates FY 2027/28 prepared and submitted to MoFPED | N/A | N/A | N/A | N/A | N/A | N/A
| Budget Framework Paper FY 2027/28 prepared and submitted | N/A | N/A | N/A | N/A | N/A | N/A
| Annual LG Budget consultative meetings participated in and reports produced | Annual LG Budget consultative meetings participated in and reports produced |  |  | Paticipated in Annual LG Budget consultative meetings in the four (4) regions across the country (Eastern, Western, Northern and Central) and a consolidated report produced. |  | Target Achieved
| Quarterly performance reports prepared and submitted on PBS | Q1 performance report prepared and submitted |  |  | Q1 performance report prepared and submitted to MOFPED through the PBS |  | Target Achieved
| Approved Budget Books for FY 2026/27 printed and disseminated | Copies of Approved Budget Books for FY 2026/27 printed and disseminated |  |  | Copies of Approved Budget Books for FY 2026/27 printed and disseminated | Not achieved | Activity rolled over to Q2
| Capacity building for 7 Planning staff undertaken in research based planning and related professional short courses | Capacity building for 7 Planning staff undertaken in research based planning and related professional short courses |  |  | Capacity building for 2 Planning staff undertaken in research based planning and related professional short courses |  | Target Achieved
| Routine Support supervision and monitoring of implementation of Ministry interventions and mandate in 40 Local Governments in four regions undertaken. | Routine Support supervision and monitoring of implementation of Ministry interventions and mandate in 10 Local Governments in Eastern region undertaken. |  |  | Routine Support supervision and monitoring of implementation of Ministry interventions and mandate in 10 Local Governments in Eastern region undertaken. |  | Target Achieved
| Planning Division annual strategic planning and prioritisation retreat held | Planning Division annual strategic planning and prioritisation meeting held |  |  | 04 annual strategic planning and prioritisation meetings held with MOLHUD staff. |  | Target Achieved
| Budget Corrigenda report FY 2027/278 prepared and submitted to MoFPED | N/A | N/A | N/A | N/A | N/A | N/A
| Quarterly Finance Committee Meetings held | Q1 Finance Committee Meeting held |  |  | Q1 Finance Committee Meeting held on 15th July 2026 |  | Target Achieved
| 12 Ministry departments trained in planning, budgeting and reporting | N/A | N/A | N/A | N/A | N/A | N/A
| Ministry Detailed budget estimates FY2027/28 prepared and submitted | N/A | N/A | N/A | N/A | N/A | N/A
| 4 Planning and Budgeting workshops undertaken | Sub-programme FY 2026/27 Budget dissemination engagements undertaken |  |  | 04 Sub-programme FY 2026/27 Budget dissemination engagements undertaken with Ministry staff.
Annual Budget | 1750000 | Quarter one budget | 440804 | 394000 |  | 394000
Key Service Area: 000027 Programme Working Group Secretariat Services; PIAP Output 10511101 Enhanced coordination and programme secretariat services | 2 SUHP Programme Planning and Budgeting meetings held. | 01 SUHP Programme Planning and Budgeting meetings held. |  |  | 02 SUHP Programme Planning and Budgeting meetings held. |  | Target Achieved
| Quarterly programme-level planning and budgeting meetings held. | Quarterly programme-level planning and budgeting meetings held. |  |  | 04 Quarterly programme-level planning and budgeting meetings held. |  | Target Achieved
| Programme vote allocations for FY 2027/28 approved and submitted to MoFPED | N/A | N/A | N/A | N/A | N/A | N/A
| 1 Sustainable Urbanization and Housing Programme Leadership meeting held | N/A | N/A | N/A | N/A | N/A | N/A
| Capacity building of staff in Programme budgeting incorporating climate and Gender specific issues conducted. | N/A | N/A | N/A | N/A | N/A | N/A
| Technical support to Leadership Committee, PWG and TWG provided. | Technical support to Leadership Committee, PWG and TWG provided |  |  | Technical backstopping provided to (03) Ministry Committees i.e Leadership committee, PWG, and the TWG |  | Target Achieved
| Inter-ministerial and inter-agency budget allocations coordinated in line with programme priorities, transparency and accountability requirements | N/A | N/A | N/A | N/A | N/A | N/A
Annual Budget | 600000 | Quarter one budget | 180000 |  |  | 180000
Key Service Area: 000039 Policies, Regulations and Standards; PIAP Output 10511201 Policy and Legal Framework developed, reviewed, and implemented (AC/Policy) | 2 Policy review meetings workshops facilitated | N/A |  |  | One Policy review meeting held to review the National Urban Policy, 2017. (A meeting was held with Urban Development Department staff to review the National Urban Policy, 2017, as part of the preparatory consultations. This was followed by a broader review meeting held at Cabinet Secretariat). | 2,700,000/= | Though policy review meeting had been planned to be carried out in quarter 2, because of its urgency by Cabinet it had to be done in quarter 1
| 4 Domestic field trips for data collection or consultations on policy issues undertaken in 5 districts in each of the 4 regions in the country | 1 Domestic field trip for data collection or consultations on policy issues undertaken in 5 districts in the eastern region |  |  | 1 domestic field trip was carried out in five districts i.e. Mbarara, Masaka, Kabaale, Jinja and Mbale MZOs to collect information on policy issues. | 20,000,000/= | Target Achieved
| 1 Cabinet Forward Agenda developed | 1 Cabinet Forward Agenda developed |  |  | 1 Cabinet forward Agenda was developed and submitted to Cabinet Secretariat. | 2,100,000/= | Target Achieved
| 12 Cabinet Memoranda prepared and submited to Cabinet | 3 Cabinet Memoranda prepared and submited to Cabinet |  |  | 3 Cabinet Memoranda were prepared and submitted to Cabinet for consideration : - i. Cabinet Memorandum on the status of International and Local Government Boundary demarcation and re-affirmation in Uganda; ii. Cabinet Memorandum on the appointment of four members of the Surveyors Registration Board; and iii. Cabinet Memorandum on the Physical Planning Bill, 2026. | 8,000,000/= | Target Achieved
| 5 Policy briefs and position papers on topical public policy issues prepared | 1 Policy brief and position paper on topical public policy issues prepared |  |  | 5 Policy briefs prepared and submitted to the Ministers on Cabinet Memoranda submitted by other MDAs covering the following matters: 1) Proposal to operationalise the issuance of Uganda's sovereign Sukuk worth EUR 405 million to finance a section of the Malaba–Kampala Standard Gauge Railway. 2) Cabinet Memorandum CT 2026 (2026–2031) No. 11 on the ratification of instruments adopted by the 24th Ordinary Meeting of the Summit of EAC Heads of State. 3) Cabinet Memorandum CT 2026 (2026–2031) No. 07 on the Uganda Railways Bill, 2026. 4) Cabinet Memorandum CT 2026 (2026–2031) No. 28 on the establishment of the Engineering Development and Innovation Centre (EDiC) as a corporation. 5) Cabinet Memorandum CT 2026 (2026–2031) No. 36 on Uganda's preparedness and responses to the impending 2026/2027 El Niño phenomenon. |  | Target Achieved
| Capacity of 7 staff strengthened in policy analysis | NPA |  |  | Capacity of two (02) staff built in policy analysis with regard to Real Estate. | 5,100,000/= | Other 5 staff their capacity will be built in the subsequent quarters
| 4 research/study report on sectoral policy issues prepared | 1 research/study report on sectoral policy issues prepared |  |  | Not done |  | Will be done in quarter 2.
| 3 Regulatory Impact Assessment Reports prepared | N/A |  |  | One Regulatory Impact Assessment RIA) on Government Land Management undertaken. | 6,400,000/= | This was done in conjunction with ULC. No variation
Annual budget | 350000 | Quarter one budget | 72682480 |  |  | 72682480 | UGX 25,032,480 spent during the quarter on periodicals, welfare, fuel, vehicle maintenance and maintenance other.
Key Service Area: 000040 Inventory Management; PIAP Output 10511610 Efficient Records management (Senior Inventory Officer) | Periodic Assessment exercises of receipt, storage and inventory accountability undertaken in the 22 Ministry Zonal Offices | Quarterly stock taking exercise conducted & amp; report produced |  |  | Quarterly stock taking exercise conducted & amp; report produced | 16310000 | Target Achieved
| Fixed Asset Management verification exercise conducted for Head office and 5 MZOs | Fixed Asset Management verification exercise conducted for Head office and 5 MZOs |  |  | Fixed Asset Management verification exercise conducted for Head office and 5 MZOs @ H/Q & Rukungiri Mbarara, Masaka, Kabale & Mpigi, MZO’s | 28780000 | Target Achieved
| Staff of 5 MZOs trained on compliance to inventory management | Staff of 5 MZOs trained on compliance to inventory management |  |  | Staff from 5 Ministry Zonal Offices – Lira, Mukono, Jinja, Tororo, Mbale, Soroti, Gulu, Arua and Moroto – trained on compliance with asset management procedures at Headquarters. | 17705000 | Target Achieved
| Bi-Annual Asset identification and engraving conducted. | N/A | N/A |  | N/A | N/A | N/A
| Capacity of 2 staff enhanced in Inventory management courses | N/A | N/A |  | N/A | N/A | N/A
Annual Budget | 350000 | Quarter one budget | 77800 |  |  | 62795000 | Inadequate funding
Key Service Area: 000051 Affiliated and professional Bodies; PIAP Output 10511604 Cross cutting issues mainstreamed (HRM) | Annual Shelter subscription paid | N/A
| Budget support to Surveyors Registration Board provided. | Budget support to Surveyors Registration Board provided |  |  | Budget support to Surveyors Registration Board not provided |  | Inadequate funds
| Budget support to Institute of Surveys and Land Management provided | Budget support to Institute of Surveys and land management provided |  |  | Budget support to Institute of Surveys and land management not provided |  | Inadequate funds
| Subscription to Regional Centre for Mapping of Resources for Development (RCMRD) paid. | N/A | N/A | N/A | N/A | N/A | N/A
Annual Budget | 516616 | Quarter one budget | 129154 |  |  | 129154
Key Service Area: 000089 Climate Change Mitigation;PIAP Output 10511604 Cross cutting issues mainstreamed (HRM) | Climate resilience integrated into the Urban Transport strategy | 2 stakeholder engagements undertaken to review urban transport strategy |  |  | Not undertaken |  | No release
| Lands, Housing and Urban Development sector Climate Action Plan Developed | Climate Action Framework for Ministry of Lands, Housing and Urban Development developed |  |  | Not undertaken |  | No release
Annual Budget | 200000 | Quarter one budget | 50000 |  |  | 0
Key Service Area: 080012 Project Management Services; PIAP Output 10511101 Enhanced coordination and programme secretariat services (AC/Planning) | Capacity of 5 staff built in investment appraisal | N/A | N/A | N/A | N/A | N/A | N/A
| Technical support provided to 12 Departments in development of bankable projects | Technical support provided to 12 Departments in development of bankable projects |  |  | Technical support provided to 03 Departments in development of bankable projects |  | Target Achieved
| 04 Project Preparation Committee (PPC) meetings held | 1 Project Preparation Committee (PPC) meetings held |  |  | Written to HODs to nominate officers to the PPC |  | Activity partially implemneted
| 12 user departments trained in use of the Integrated Bank of Projects (IBP) | N/A | N/A | N/A | N/A | N/A | N/A
| 4 staff trained in Project Management Professional course (PMP | 01 staff trained in Project Management Professional course (PMP) |  |  | 01 staff trained in Project Management Professional course (PMP) |  | Target Achieved
| Capacity of 5 staff built in investment appraisal | N/A | N/A | N/A | N/A | N/A | N/A
| Quarterly performance reports for Ministry projects prepared | Q1 performance reports for Ministry projects prepared |  |  | Q1 performance reports for Ministry projects prepared |  | Target Achieved
| Multiyear commitments for FY2027/28 report prepared | N/A | N/A | N/A | N/A | N/A | N/A
Annual Budget | 519237 | Sub total | 129809 |  |  | 129809

## Sheet1
NDPIV OBJECTIVE | PIAP RESULT | Key output | Activity | Activity Cost | Source of Funding
Develop and maintain Urban Infrastructure in line with Physical Development Plans | Improved urban infrastructure | Detailed Physical Development Plans developed for respective local governments | Identify, prioritise and conduct stakeholder consultations and community sensitization on detailed physical development planning in LGs
Support Preparation of detailed land-use, zoning and development-control plans and draft detailed Physical Development Plans (DPDPs) for selected LGs
Support Processing of plans for approval by the relevant planning authorities.
Support implementation and enforcement of the approved plans
Monitor compliance and periodically review/update the Detailed Physical Development Plans
| Increased compliance with land use in urban areas | Urban Councils Complying to Land Use Regulatory Framework | Identify and Sensitize communities and developers on land-use regulations.
Train physical planners and development-control personnel.
Provide technical support and backstopping to Local Governments.
Conduct field inspections and compliance assessments.
Prepare and submit compliance reports
Enforce adherence to approved physical development plans.
Disseminate physical planning standards and guidelines.
City/Municipal/Town Council physical development plans developed/implemented.
Detailed physical development plans developed for selected cities and local governments.
Cities/Municipalities/ Town councils compliance with physical planning guidelines andstandards and approved physical development plans.
Develop sustainable waste management systems | Improved livability and cleanliness of urban areas |  | Waste management systems established | Develop and enforce the Waste Management Policy.
|  |  | Air quality improved | Develop and implement municipal and citywide waste master plans.
|  |  | Land tenure security improved | Implement the 4R waste management model — Reduce, Reuse, Recycle and Recover — in residential and commercial settings.
Establish and/or improve gazetted solid waste disposal sites in urban local governments.
Promote decent housing for the different income segments. |  |  |  | Develop and improve waste collection, transportation and disposal systems.
Promote waste segregation at source in residential, commercial and institutional areas.
Promote waste recovery, recycling and resource recovery facilities.
Strengthen capacity of Cities, Municipalities and urban Local Governments to manage solid waste.
Promote private-sector and community participation in waste management.
Monitor and enforce compliance with waste management standards and regulations.
Monitor implementation of waste management strategies and plans in Cities and Municipalities.
Increase economic opportunities in urban areas. |  |  |  | Rehabilitate and improve existing waste management facilities where required.
Strengthen the policy, legal, institutional, and coordination frameworks.

## Sheet2
Strategic Objective | Expected Result/outcome | Output | Key Activities/Actions (Quantified, location,period) | Cost UGX ,000 | Source of Funding
Strengthen and implement efficient land administration and management systems | Improved land Tenure Security Key Indicators 1. % Land surveyed 2. Turnround time (days) for titling; 3. % Land RegistereS | PIAP Output 06511101 NRECCLWM programme Policy frameworks developed/reviewed | Land related laws (Land Act, Land regulations and guidelines, RTA, Surveyors Act, Surveyor Registration Act) reviewed |  |  | 1
ADR guidelines on settling disputes on Customary land and other land tenures validated and disseminated in the 4 regions
Land related laws, policies, and guidelines disseminated in 50 District Local governments
40 Statutory Instruments for land acquisition drafted and issued
Revised National Land Policy,2025 disseminated
Land related laws, policies, and guidelines disseminated in 50 District Local governments
|  | Sub Total |  | 362100
|  | PIAP Output 06611101 Land Management and Valuation infrastructure enhanced | 500 Land Management institutions trained in land management
100 Land Management institutions supervised and inspected
50 DLBs vetted and approved
Membership dues to Uganda Law society and East African Law society paid
40 Land Dispute redress Committees in 40 Districts trained in ADR mechanisms
80 land transactions inspected for compliance with established legal and administrative standards
-Communities in Obongi and Rukiga mobilized and sensitized on SLAAC
22 MZOs in Central, Western, Northern and Eastern regions monitored and inspected.
-80 land transactions inspected for compliance with established legal and administrative standards.
Capacities of departmental staff enhanced in ADR in land management and best practices.
Local leaders and mediators in 40 Districts trained land dispute resolution.
Study on the effect of Certificates Of Occupancy on Mailo Land undertaken and report produced
Study undertaken on post issuance transactions for Certificates of Customary Ownerships and report produced
|  | Sub Total |  | 742000
Total-Land Administration |  |  |  | 1104000 | NWR
|  | PIAP Output 06611101 Land Management and Valuation infrastructure enhanced & PIAP Output 06611102 Land Surveys and registration programs implemented | -MLHUD IT Strategic Plan developed
Quarterly Uganda National Land Information System (UgNLIS) Performance reports produced and disseminated
MLHUD IT Strategic Plan developed
Microsoft 365 services for IT management services procured
-Redundant UgNLIS Links established in 10 MZOs
UgNLIS Security Operational Center (SOC) established and linked to the system across all MZOs
Customer Care service centre improved and upgraded to support the Public on Land Services
UgNLIS System upgrades tested and deployed in all MZOs
Routine maintenance of the MZOs IT infrastructure and UgNLIS system undertaken
Quarterly LAVMIS reports produced
20 staff trained and certified in IT courses i.e., ITIL/COBIT
MLHUD IT Risk management framework developed
UgNLIS Connectivity to Uganda Telecommunications Company Limited paid
Network Infrastructure upgraded to support UgNLIS service availability
Automatic Voltage Regulator procured to protect UgNLIS equipment
UgNLIS SMS alerts/ Notifications procured
22 MZOs monitored and provided with technical support
Performance review workshop for 60 IT staff (NLIC and MZOs) to strengthen capacity on merging technologies including blockchain and enhance delivery of ICT services conducted.
Production of 40,000 Titles supported
Processing of 20,000 Certificates of Customary Ownership (CCOs) supported.
|  | Sub Total |  | 8500000
Total land sector Reform |  |  |  | 8500000
|  | PIAP Output 06511101 NRECCLWM programme Policy frameworks developed/reviewed | -Registration of Titles Act amended
Trustees In cooperation Act ammended
|  | Sub Total |  | 220000
|  | PIAP Output 06611102 Land Surveys and registration programs implemented | -100,000 search letters issued from the Land Information System
1200 court case litigated for both male and female clients
300 public hearings conducted for all categories of clients including the elderly and Persons With Disability
Production of 40,000 Titles supported
Two multi-sectoral engagements undertaken on Improving Land Registration processes
Specialized Attire acquired for 10 Registrars of titles for attending court (flaps, gowns, shirts, file carrier bags)
40000 land titles issued to men, women and PWD's
Land registration activities in 22 MZOs monitored and supervised
80 Trustees registered
40 Land registrars from both Ministry Zonal Offices and Headquarters trained on best practices in land registration and continuous legal education with Uganda Law Society (ULS)
Subscription paid for renewal of practicing certificates for 20 Registrars
-31 land titles issued in fragile ecosystems (wetlands and forest reserves) investigated
2 Performance review workshops for Registrars of Titles undertaken
1 Project concept developed
Benchmarking visits on improving Land Management systems undertaken for 2 Department staff
|  | Subtotal |  | 878000
Total for land Registration |  |  |  | 1098000
PIAP Output 06511101 NRECCLWM programme Policy frameworks developed/reviewed
3 stakeholders engagements carried out on Survey and Mapping Bill, Survey Reports standards and National Mapping Standards developed.
| Sub total |  |  | 200000
|  | PIAP Output 06611102 Land Surveys and registration programs implemented | 500 copies of Maps for district and City Administrative Units printed and disseminated
100 copies of Tourist Map for Entebbe Municipality and Jinja City produced, printed and disseminated
Digitization and integration of large scale maps for 3 cities of Masaka, Soroti, Mbale and Masindi Municipality carried out
20kms Surveyed for Moroto Napak inter-district boundaries to reduce boundary disputes
6 International Boundary re-affirmation meetings held to reduce border disputes
54 Thematic maps revised for 6 districts (Nakaseke, Luwero, Nakasongola, Kiboga, Mityana & Kyankwanzi)
Restructuring of sixty (60) Mbarara ranches for automation of plot numbers and harmonization of five (5) overlapping blocks for Mukono & Kyadondo
20 Topographic Maps at the scale of 1:50,000 for Greater Kampala vectorized and updated
National Atlas revised
| Sub total |  |  | 1334700
Tota for Surveys and Mapping |  |  |  | 1534700
|  | PIAP Output 06611101 Land Management and Valuation infrastructure enhanced | Compensation rates for 135 districts reviewed
40 District Land Boards trained on the used of the Compensation rates database
Capacity of 15 Valuation Staff built in Valuation competencies
-80,000 property valuations carried out and supervised
Valuation activities Monitored in the 22 Ministry Zonal Offices
| sub total |  |  | 1173000
|  | valuation Project; PIAP Output 06611101 Land Management and Valuation infrastructure enhanced | 24 Handheld equipment (tablets) procured for rollout of Land Valuation Management Information System
Land Valuation Management Information System rolled out in 22 Ministry Zonal Offices
Property land value trend analysis conducted for 2 districts; Gulu and Jinja.
Land Valuation Management Information system and infrastructure maintained in all MZOs
Refresher trainings on navigation of LAVMIS undertaken for 40 Valuers at Headquarters and the Ministry Zonal Offices
-02 Regional Stakeholder engagements undertaken for external users of LAVMIS in Western and Northern regions
Valuation Act 2025 gazetted
500 copies of the Valuation Act 2025 produced
Valuation Regulations developed
Financial support 200m provided for the establishment of the Institute of Certified Valuers
Countrywide market research on land values undertaken
Improve intergrated land use planning, implementation and development systems in rural and urban areas | Orderly Development | %level of compliance to landuse frameworks |  |  |  | 1. Physical Planning; 2. Land Use Regulation, Compliance and Enforcement; 3. MZOs; 4. UCMID
Develop livable, productive, inclusive, environmentally resilient urban systems | Orderly Development | %level of compliance to landuse frameworks
Develop and implement housing dwliveery programs and real estate bmarket systems | Increased housing stock | %reduction in housing deficit |  |  |  | 1. Human settlements; 2. Housing and Real Estate Management
Strengthen policy, legal, institutional and coordination frameworks | Harmonised planning and implementation frameworks | % increase in performance of the Ministry | 22 MZO vehicles serviced and maintained |  |  | 1. Finance and Administration; 2.Statistics, Research, Monitroring and Evaluation 3. LECP