MINISTRY OF LANDS, HOUSING AND URBAN DEVELOPMENT

GULU MZO QUARTER ONE PERFORMANCE REPORT FOR FY 2026/2027

Department: MINISTRY ZONAL OFFICES

| KEY SERVICE AREA/PIAP output | Annual Output | Planned Q1 Target | Approved budget | Warrants |  | Achieved Q1 physical performance | Amount Spent | Reasons for Variation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Key Service Area: 000039 Policies, Regulations and Standards; PIAP Output 10511201 Policy and Legal Framework developed, reviewed, and implemented (PAS)O | Capacity building of Land Management Institutions (LMIs) | 01 Capacity building meeting undertaken | 4,900,000/= | 3,100,000/= |  | 01 capacity building meeting for LMIs held for Nwoya District, Anaka, Koch-Goma & Purongo TCs | 3,100,000/= | Limited funds |
|  | 04 Barazas & Exhibition organized at the MZOs on land management issues. and to sensitize the public on Ministry services | 01 Baraza & Exhibition organized at Nwoya district on land management & registration processes | - | - |  | Not organized | - | No funds |
|  | 03 MZO end of month meetings held | 03 MZO monthly meetings held | 4,800,000/= | 4,800,000/= |  | 03 end of month meetings held (July, August & September) | 4,800,000/= |  |
|  | 04 Locus visits and boundary opening undertaken within the MZOs’ jurisdictions | 01 Locus visit and boundary opening undertaken within the MZOs’ jurisdictions | 7,670,455/= | 1,815,000/= |  | 01 Locus visit undertaken in Lamwo | 1,815,000/= | Limited funds |
|  | Sensitization & Promotional items procured | 2,052 Brochures for sensitization procured | 8,181,818/= | 4,104,000/= |  | 2,052 Brochures for sensitization procured | 4,104,000/= | Limited funds |
|  | Capacity building of MZO staff undertaken | Capacity building of MZO staff undertaken | 6,136,364 | 3,077,187= |  | Training of MZO staff in Customer care service conducted | 3,077,187/= | Limited funds |
|  | 04 Annual subscriptions made to professional bodies | 01 Annual subscription made to a professional body | - | - |  |  |  | Budget consideration recommended |
|  | Minor civil repairs of the MZO structures undertaken | 01 Office block repaired (administration block) | 22,500,000/= | 11,283,019= |  | Civil repairs for the structure, Plumbing, Curtain rails procured, Bio-metric doors, office doors, office chairs | 11,283,019= | Insufficient funds to cater for painting |
|  | Office Imprest |  | 3,100,000/= | 3,100,000/= |  | Office Imprest to support office administration | 3,100,000/= |  |
|  | Periodicals/ Newspapers procured | Quarterly periodicals | 1,161,800/= | - |  |  |  | Not paid |
|  | Annual Revenue Generated within the MZO's jurisdiction | Q1 revenue of UGX 473,000,000 collected |  |  |  |  |  |  |
|  | 04 radio talk shows held on Land Management | 01 radio talk show held on Land Management | - | - |  | - |  | Airtime already booked by MDAs |
|  | National Land Valuation Management Information System (N-LaVMIS) managed | 01 Training session and rolling out of N-LaVMIS undertaken | - | - |  | 02 Valuers & 08 District Land Officers trained in N-LaVMIS | - |  |
|  | 20 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken | 05 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken | - | - |  | 5 ADR meetings undertaken |  | Need to budget for ADR meetings |
|  | 20 Court cases litigated | 05 Court cases litigated | - | - |  | 05 court cases litigated | - | Budget consideration recommended |
|  | 20,000 titles produced and issued, including SLAAC | 5,000 titles produced and issued, including SLAAC | - | - |  | 560 Land titles produced | - |  |
|  | MZO equipment serviced and maintained, including computers, printers and scanners | MZO office equipment (computers) serviced | Not budgeted | N/A |  | N/A |  | Budget consideration recommended |
|  | MZO Vehicles serviced and maintained | 02 MZO Vehicles serviced and maintained | 10,227,273/= | 5,128,645/= |  | MZO vehicle serviced and maintained | 5,128,645= | Insufficient funds |
|  | Staff team-building, health and wellness activities conducted | 01 staff team-building and wellness sessions conducted | - | - |  | - | - |  |
|  | Gender, HIV/AIDS, environment and other crosscutting issues mainstreamed | 100 condoms supplied to staff 02 awareness activities conducted | N/A |  |  | N/A |  | Budget for Gender & HIV issues recommended |
|  | 01 Land awareness week conducted | 05 Stakeholder engagements conducted | N/A | N/A |  |  |  | Budget recommended |
|  | Finance Committee Meetings and general movement facilitated | 03 Finance Committee Meetings facilitated | 7,670,455/= | 1,381,084/= |  | 03 Financed Committee meeting facilitated | 1,381,084/= |  |
|  | Allowance for non-science staff | 03 Staff allowances paid | 8,181,818/= | 4,102,916/= |  | 03 non-science Staff allowances paid | 4,102,916/= | Limited funds |
|  | Fuel, Oil & Lubrication |  | 16,363,636/= | 8,205,832/= |  |  | 8,205,832/= | Insufficient funds |
|  | Facilitation for clearance of backlog |  | 3,161,000/= | - |  |  |  | Not paid |
|  | Sub-Total |  | 100,954,619= | 50,097,683= |  |  | 50,097,683= |  |
|  | Total |  |  |  |  |  |  |  |

Name:	 Ssenteza Jude Tadeo				Signature:					Date: 	12/10/2026

Head of Department/Project Coordinator/MZO Head

Attach signed departmental minutes