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MINISTRY OF LANDS, HOUSING AND URBAN DEVELOPMENT
QUARTER ONE PERFORMANCE REPORT FOR FY 2026/2027

Department: MINISTRY ZONAL OFFICES/JINJA
	[bookmark: _Hlk242254448]KEY SERVICE AREA/PIAP output
	Annual Output 
	Planned Q1 Target   
	Approved budget
	Warrants
	
	Achieved Q1 physical performance
	Amount Spent
	Reasons for Variation 

	Key Service Area: 000039 Policies, Regulations and Standards; PIAP Output 10511201 Policy and Legal Framework developed, reviewed, and implemented (PAS)
	04 Barazas organized at the MZOs on land management issues. and to sensitize the public on Ministry services
	01 Baraza organized at the MZOs on land management issues. and to sensitize the public on Ministry services
	9,598,000
	
	
	01 Baraza held at the Mzo on 7/10/2026
	9,598,000
	…

	
	04 Locus visits and boundary opening undertaken within the MZOs’ jurisdictions
	 Locus visit and boundary opening undertaken within the MZOs’ jurisdictions
	
	
	
	2 Locus visits undertaken
	2,391,967
	

	
	Capacity building of  MZO staff undertaken in various fields.
	Kiswahili Lessons conducted at the Mzo for three months.
	3,077,187
	
	
	Not undertaken as funds were not released for it
	0
	

	
	04 Annual subscriptions made to professional bodies
	01 Annual subscription made to a professional body
	400,000
	
	
	Administrative Officer’s forum Subscription paid
	400,000
	

	
	Minor civil repairs of the MZO structures undertaken
	01 office block painted (administration block)
	7,000,000
	
	
	Not Undertaken because the funds were not released,
	0
	

	
	Annual Revenue Generated within the MZO's jurisdiction
	Q1 revenue of UGX ……… collected
	
	
	
	
	
	

	
	04 radio talk shows held on Land Management
	01 radio talk show held on Land Management
	NA
	
	
	
	
	

	
	National Land Valuation Management Information System (N-LaVMIS) managed
	01 Training session and rolling out of N-LaVMIS undertaken 
	NA
	
	
	
	
	

	
	04 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken
	01 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken
	NA
	
	
	
	
	

	
	12 Court cases litigated
	03 Court cases litigated
	NA
	
	
	
	
	

	
	51,482 titles produced and issued, including SLAAC
	12,870  titles produced and issued, including SLAAC
	
	
	
	13,878 SLAAC Titles delivered to District HQs for on ward delivery to the final beneficiaries
Luuka                =   7,506
Kamuli              =    3,963
Mayuge             =       658
Namutumba       =   1,169
Jinja City            =      582
	2,845,000
	

	
	MZO equipment serviced and maintained, including computers, printers and scanners
	MZO office equipment (computers) serviced
	NA
	
	
	
	
	

	
	MZO Vehicles serviced and maintained
	01 MZO Vehicles serviced and maintained
	5,128,645
	
	
	01 Mzo vehicle serviced and maintained
	5,128,645
	

	
	Staff team-building, health and wellness activities conducted
	01 staff team-building and wellness sessions conducted
	NA
	
	
	
	
	

	
	Gender, HIV/AIDS, environment and other crosscutting issues mainstreamed
	100 condoms supplied to staff

02 awareness activities conducted 
	NA
	
	
	
	
	

	
	01 Land awareness week conducted 
	05 Stakeholder engagements conducted
	NA
	
	
	
	
	

	
	Finance Committee Meetings facilitated
	01 Finance Committee Meetings facilitated
	
	
	
	
	
	

	
	
	Plumbing and sanitary system repaired
	2,786,029
	
	
	Not Conducted
	0
	Funds not released

	
	
	Electrical faults fixed
	1,497,000
	
	
	Not conducted
	0
	Funds not released.

	
	
	Advertisement and Public relations conducted
	4,102,916
	
	
	Not conducted
	0
	Funds not released.

	
	Sub-Total
	
	
	
	
	
	……..
	

	
	Total 
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