MINISTRY OF LANDS, HOUSING AND URBAN DEVELOPMENT

QUARTER ONE PERFORMANCE REPORT FOR FY 2026/2027

Department: MINISTRY ZONAL OFFICES/JINJA

| KEY SERVICE AREA/PIAP output | Annual Output | Planned Q1 Target | Approved budget | Warrants |  | Achieved Q1 physical performance | Amount Spent | Reasons for Variation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Key Service Area: 000039 Policies, Regulations and Standards; PIAP Output 10511201 Policy and Legal Framework developed, reviewed, and implemented (PAS) | 04 Barazas organized at the MZOs on land management issues. and to sensitize the public on Ministry services | 01 Baraza organized at the MZOs on land management issues. and to sensitize the public on Ministry services | 9,598,000 |  |  | 01 Baraza held at the Mzo on 7/10/2026 | 9,598,000 | … |
|  | 04 Locus visits and boundary opening undertaken within the MZOs’ jurisdictions | Locus visit and boundary opening undertaken within the MZOs’ jurisdictions |  |  |  | 2 Locus visits undertaken | 2,391,967 |  |
|  | Capacity building of MZO staff undertaken in various fields. | Kiswahili Lessons conducted at the Mzo for three months. | 3,077,187 |  |  | Not undertaken as funds were not released for it | 0 |  |
|  | 04 Annual subscriptions made to professional bodies | 01 Annual subscription made to a professional body | 400,000 |  |  | Administrative Officer’s forum Subscription paid | 400,000 |  |
|  | Minor civil repairs of the MZO structures undertaken | 01 office block painted (administration block) | 7,000,000 |  |  | Not Undertaken because the funds were not released, | 0 |  |
|  | Annual Revenue Generated within the MZO's jurisdiction | Q1 revenue of UGX ……… collected |  |  |  |  |  |  |
|  | 04 radio talk shows held on Land Management | 01 radio talk show held on Land Management | NA |  |  |  |  |  |
|  | National Land Valuation Management Information System (N-LaVMIS) managed | 01 Training session and rolling out of N-LaVMIS undertaken | NA |  |  |  |  |  |
|  | 04 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken | 01 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken | NA |  |  |  |  |  |
|  | 12 Court cases litigated | 03 Court cases litigated | NA |  |  |  |  |  |
|  | 51,482 titles produced and issued, including SLAAC | 12,870 titles produced and issued, including SLAAC |  |  |  | 13,878 SLAAC Titles delivered to District HQs for on ward delivery to the final beneficiaries Luuka = 7,506 Kamuli = 3,963 Mayuge = 658 Namutumba = 1,169 Jinja City = 582 | 2,845,000 |  |
|  | MZO equipment serviced and maintained, including computers, printers and scanners | MZO office equipment (computers) serviced | NA |  |  |  |  |  |
|  | MZO Vehicles serviced and maintained | 01 MZO Vehicles serviced and maintained | 5,128,645 |  |  | 01 Mzo vehicle serviced and maintained | 5,128,645 |  |
|  | Staff team-building, health and wellness activities conducted | 01 staff team-building and wellness sessions conducted | NA |  |  |  |  |  |
|  | Gender, HIV/AIDS, environment and other crosscutting issues mainstreamed | 100 condoms supplied to staff 02 awareness activities conducted | NA |  |  |  |  |  |
|  | 01 Land awareness week conducted | 05 Stakeholder engagements conducted | NA |  |  |  |  |  |
|  | Finance Committee Meetings facilitated | 01 Finance Committee Meetings facilitated |  |  |  |  |  |  |
|  |  | Plumbing and sanitary system repaired | 2,786,029 |  |  | Not Conducted | 0 | Funds not released |
|  |  | Electrical faults fixed | 1,497,000 |  |  | Not conducted | 0 | Funds not released. |
|  |  | Advertisement and Public relations conducted | 4,102,916 |  |  | Not conducted | 0 | Funds not released. |
|  | Sub-Total |  |  |  |  |  | …….. |  |
|  | Total |  |  |  |  |  |  |  |

Name:										Signature:					Date:

Head of Department/Project Coordinator/MZO Head

Attach signed departmental minutes