MINISTRY OF LANDS, HOUSING AND URBAN DEVELOPMENT

QUARTER ONE PERFORMANCE REPORT FOR FY 2026/2027
Department: MINISTRY ZONAL OFFICES (KABAROLE MZO)
	KEY SERVICE AREA/PIAP output
	Annual Output 
	Planned Q1 Target   
	Approved budget
	Warrants
	
	Achieved Q1 physical performance
	Amount Spent
	Reasons for Variation 

	Key Service Area: 000039 Policies, Regulations and Standards; PIAP Output 10511201 Policy and Legal Framework developed, reviewed, and implemented (PAS)
	6 sensitization meetings land administration issues and compliancy issues organized in six local governments 
	2 sensitization meetings at Kyegegwa District local Government about land administration and compliancy issues 
	8,181,818/=
	4,102,915.95/=
	
	2 sensitization meetings carried out at Kyegegwa District local government on land administration and compliancy
	5,300,000 /=
	The activity had already been planned and could not be re planned to fit in the allocated amount.

	
	04 Locus visits and boundary opening undertaken within the MZOs’ jurisdictions
	 04 Locus visits conducted by registrar and Land officer in Bundibugyo district  
	15,340,909/=
	7,692,967.41/=
	
	
	2,400,000/=
	Money requested by valuation officer Mr. joakim Mbale, physical planner Mr Andrew Okiror and surveyor Peter Wanyama was never advanced to the said officers for filed activities

	
	Capacity building of MZO staff undertaken in various fields.
	Capacity building of 8 MZO staff undertaken in various fields.
	6,136,364/=
	3,077,186.96/=
	
	Capacity building of 8 MZO staff undertaken in trouble shooting frequently occurring errors on the NLIS
	3,009,000 /=
	Minor

	
	04 Annual subscriptions made to professional bodies
	01 Annual subscription made to a professional body
	
	
	
	
	
	

	
	Minor civil repairs of the MZO structures undertaken
	01 office block plumbing fixed, seater toilets replaced, metallic curtain loads and curtain clothes, lighting system repaired and fixed
	22,500,000/=
	11,283,018.87/=
	
	plumbing system repaired, metallic curtain rods fixed.
	4,927,000 /=
	Money for the purchasing and fixing of curtains cloth and netting material worthy 7
,000,000 /= requested for not yet reflected on the account of PAS Ntegeka Desteao

	
	Annual Revenue Generated within the MZO's jurisdiction
	Q1 revenue of UGX 473,000,000 collected
	
	
	
	
	
	

	
	04 radio talk shows held on Land Management
	01 radio talk show held on Land Management
	
	
	
	
	
	

	
	National Land Valuation Management Information System (N-LaVMIS) managed
	01 Training session and rolling out of N-LaVMIS undertaken 
	
	
	
	
	
	

	
	04 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken
	01 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken
	
	
	
	
	
	

	
	12 Court cases litigated
	03 Court cases litigated
	
	
	
	
	
	

	
	20,000 titles produced and issued, including SLAAC
	5,000 titles produced and issued, including SLAAC
	
	
	
	
	
	

	
	MZO equipment serviced and maintained, including computers, printers and scanners
	MZO office equipment (computers) serviced
	
	
	
	
	
	

	
	MZO Vehicles serviced and maintained
	02 MZO Vehicles serviced and maintained
	10,227,273
/=
	5,128,644.94/=
	
	UG0235L serviced and fully maintained now motorable 
	4,870,000/=
	Balance to be carried to the next Quarter for further maintenance 

	
	Staff team-building, health and wellness activities conducted
	01 staff team-building and wellness sessions conducted
	
	
	
	
	
	

	
	MZO staff on official duties, workshops, and seminars facilitated  
	All staff travels on official duties facilitated

	25,568,182/=
	12,821,612.35/=
	
	
	10,870,000/=
	Requisitions by Staff not yet approved

	
	01 Land awareness week conducted 
	05 Stakeholder engagements conducted
	
	
	
	
	
	

	
	Finance Committee Meetings facilitated
	01 Finance Committee Meetings facilitated
	
	
	
	
	
	

	
	Staff welfare maintained
	Daily teas and refreshments provided to staff, and pantry well maintained
	
	
	
	
	2,560,000/=
	

	
	Allowances
	Allowances for casuals temporary and sitting allowances paid
	8,181,818/=
	4,102,915.15
	
	Allowances for all staff who are non-scientists and whose salaries are not enhanced paid (managed from the headquater)
	4,102,915.95/=
	

	
	Fuel lubricants and oils
	Fuel lubricants and oil supplied to facilitate MZO activities
	16,363,636/=
	8,205,831.90/=
	
	Fuel lubricants and oils for the MZO vehicles and generator supplied by VIVO
	8,205,000/=
	

	
	Sub-Total
	
	112,500,000/=
	56,415,094/=
	
	
	46,243,915.95/=
	Some requisitions for staff activities, purchase and installation of curtain cloth and nets not yet paid

	
	Total 
	
	
	
	
	
	
	


Name
:
NTEGEKA DESTEO 
Signature:




Date: 5TH /10/2026

Head of Department/Project Coordinator/MZO Head                                                      

� Attach signed departmental minutes 
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