MINISTRY OF LANDS, HOUSING AND URBAN DEVELOPMENT

QUARTER ONE PERFORMANCE REPORT FOR FY 2026/2027

Department: KIBAALE MINISTRY ZONAL OFFICE

| KEY SERVICE AREA/PIAP output | Annual Output | Planned Q1 Target | Approved budget | Warrants |  | Achieved Q1 physical performance | Amount Spent | Reasons for Variation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Key Service Area: 000039 Policies, Regulations and Standards; PIAP Output 10511201 Policy and Legal Framework developed, reviewed, and implemented (PAS) | 04 Barazas organized at the MZOs on land management issues. and to sensitize the public on Ministry services | 01 Baraza organized at the MZOs on land management issues and to sensitize the public on Ministry services |  | 4,800,000 |  | 01 community/ and stakeholder engagement meeting held in Kagadi district | 4,800,000 |  |
|  | 04 Locus visits and boundary opening undertaken within the MZOs’ jurisdictions | 01 Locus visit and boundary opening undertaken within the MZOs’ jurisdictions |  |  |  |  |  |  |
|  | Capacity building of 08 MZO staff undertaken in various fields. | Capacity building of 02 MZO staff undertaken in various fields. | 24545454.55 | 3,077,186.96 |  | 15 staff members underwent training on Understanding the Public Service: Roles, obligations and conduct of a public officer and 3 new staff inducted | 3,080,000 | There was a general gap among all staff on understanding how Public Service operates |
|  | 04 Annual subscriptions made to professional bodies | 01 Annual subscription made to a professional body |  |  |  |  |  |  |
|  | Minor civil repairs of the MZO structures undertaken | 01 office block painted (administration block) | 90000000 | 11,283,018 |  | Office premises fumigated; Plumbing system repaired; 15 Filing cabins, 04 furniture & fittings repaired | 11,283,000 |  |
|  | Annual Revenue Generated within the MZO's jurisdiction | Q1 revenue of UGX 473,000,000 collected |  |  |  |  |  |  |
|  | 04 radio talk shows held on Land Management | 01 radio talk show held on Land Management | 32727272.73 | 4,102,915.95 |  | 01 Radio Talk show held including running advertisements | 4,102,900 |  |
|  | National Land Valuation Management Information System (N-LaVMIS) managed | 01 Training session and rolling out of N-LaVMIS undertaken |  |  |  |  |  |  |
|  | 04 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken | 01 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken |  |  |  |  |  |  |
|  | 12 Court cases litigated | 03 Court cases litigated |  |  |  |  |  |  |
|  | 20,000 titles produced and issued, including SLAAC | 5,000 titles produced and issued, including SLAAC |  |  |  |  |  |  |
|  | MZO equipment serviced and maintained, including computers, printers and scanners | MZO office equipment (computers) serviced |  |  |  |  |  |  |
|  | MZO Vehicles serviced and maintained | 02 MZO Vehicles serviced and maintained | 40909090.91 | 5,128,644.94 |  | 01 vehicle (UG 0197L) serviced and repaired | 5,128,000 |  |
|  | Staff team-building, health and wellness activities conducted | 01 staff team-building and wellness sessions conducted |  |  |  |  |  |  |
|  | Gender, HIV/AIDS, environment and other crosscutting issues mainstreamed | 100 condoms supplied to staff 02 awareness activities conducted |  |  |  |  |  |  |
|  | 01 Land awareness week conducted | 05 Stakeholder engagements conducted |  |  |  |  |  |  |
|  | Finance Committee Meetings facilitated | 01 Finance Committee Meeting facilitated |  | 990,000 |  | Q1 Finance Committee Meeting attended at Ministry Headquarters | 990,000 |  |
|  | Consolidated allowances for staff paid | Q1 consolidated allowances paid | 32727272.73 | 4,102,915.95 |  | Staff quarterly consolidated allowances paid | 5,802,000 | Warranted amount was less than the actual required amount. Difference covered under Workshops, meetings and seminars |
|  | Fuel, Lubricants and Oils paid | Fuel, oils &lubricants for daily running and generator provided | 65454545.45 | 8,205,831.90 |  | Fuel and lubricants for day- to -day operations and running the generator provided | 8,205,800 |  |
|  | Quarterly Official travels for meetings and other engagements undertaken | At least 06 official travels to Headquarters/Kampala |  | 6,940,000 |  | 06 official meetings attended at Ministry headquarters | 6,940,000 |  |
|  | Annual Public Administrative Officers’ Forum attended | 01 Administrative Officers’ forum attended |  |  |  | Annual Administrative Officers’ forum 2026 attended in Gulu City | 3,420,000 |  |
|  | Office Imprest provided | Monthly Imprest processed |  |  |  | Imprest for Q1 provided | 1,471,600 |  |
|  | Court documents verified | All court orders, letters of administration verified |  |  |  | All court orders & letters of administration verified before implementation | 1,192,000 |  |
|  | Sub-Total |  | 450,000,000 | 56,415,094 |  |  | 56,415,300 |  |
|  | Total |  |  |  |  |  |  |  |

Name:	 Barbara Nancy Asasira	Signature:					Date: 13/10/2026

Head of Department/Project Coordinator/MZO Head

Attach signed departmental minutes