MINISTRY OF LANDS, HOUSING AND URBAN DEVELOPMENT

QUARTER ONE PERFORMANCE REPORT FOR FY 2026/2027

Department: Land Administration

| PIAP output | Annual Output | Planned Q1 Target | Approved Q1 Budget (UGX) | Q1 Warrants (UGX) | Achieved Q1 physical performance | Amount spent (UGX) | Reasons for Variation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Key Service Area: 000078 Land Management PIAP OUTPUT: 10030101 Land management infrastructure enhanced | 500 Land Management institutions trained in land management. | 125 Land Management institutions in Eastern region trained in land management |  |  | 121 Land Management institutions trained; 25 DLBs, DLOs, 96 ALCs and Recorders in Jinja,Luuka, Kamuli, Iganga, Mayuge, Kaliro, Bugiri, Namayingo, Busia, Tororo, Butaleja, Budaka, Kibuku, Pallisa, Mbale, Namisindwa, Sironko, Bulambuli, Kapchorwa, Bukwo, Kumi, Bukedea, Serere, Soroti |  | … |
|  | -100 Land Management institutions supervised and inspected | -25 Land Management institutions in Eastern region supervised and inspected |  |  | 20 Land Management institutions supervised and inspected; 5 DLBs and 15 ALCs and Recorders Supervised and inspected land management institutions in Bugweri, Buyende, Kapelebyong, Katakwi, Amuria |  |  |
|  | -50 DLBs vetted and approved | -12 DLBs vetted and approved |  |  | 7 DLBs vetted; 1 DLB (Rubanda) approved, 6 DLBs (Mubende, Kabarole, Amuria, Hoima, Maracha, Mityana) pending approval. |  |  |
|  | -40 Land Dispute redress Committees in 40 Districts trained in ADR mechanisms. | -10 Land Dispute redress Committees in 10 Districts in Northern Uganda trained in ADR mechanisms |  |  | 10 Land Dispute Redress Committees in Pakwach, Zombo, Maracha, Koboko, Yumbe, Obongi, Moyo, Adjumani districts trained. |  |  |
|  | -Membership dues to Uganda Law society and East African Law society paid. | N/A |  |  | N/A |  |  |
|  | -80 land disputes investigated and reports prepared. | -20 land disputes investigated and reports prepared. |  |  | 35 land Disputes and complaints handled/ investigated and 15 pending final reports |  |  |
|  | -Capacities of departmental staff enhanced in ADR in land management and best practices. | N/A |  |  | N/A |  |  |
|  | -22 MZOs in Central, Western, Northern and Eastern regions monitored and inspected. | -03 MZOs in Northern region monitored and inspected. |  |  | 3 MZOs of Gulu, Arua, & Lira monitored and inspected to assess whether the MZOs are carrying out their statutory land administration and management responsibilities effectively, efficiently and in line with applicable laws, policies and procedures. |  |  |
|  | -80 land transactions inspected for compliance with established legal and administrative standards. | -20 land transactions inspected for compliance with established legal and administrative standards. |  |  | 20 Land transactions inspected for compliance with established legal and administrative standards in the districts of Lamwo, Mubende, Lwengo , Kyotera and Wakiso |  |  |
|  | -Local leaders and mediators in 40 Districts trained land dispute resolution. | -Local leaders and mediators in 10 Districts in Northern region trained land dispute resolution |  |  | Trained local leaders and mediators in 12 districts Oyam, Lira, Gulu, Omoro, Nwoya, Amuru, Pader, Agago, Kitgum, Lamwo, Terego, Arua |  |  |
|  | - Study on the effect of Certificates Of Occupancy on Mailo Land undertaken and report produced. | Procurement of consultant |  |  | TORs for the consultant to undertake the Study on the effect of Certificates of Occupancy on Mailo Land developed. |  |  |
|  | - Study undertaken on post issuance transactions for Certificates of Customary Ownerships and report produced | Procurement of consultant |  |  | TORs for the consultant to undertake the study on post issuance transactions for Certificates of Customary Ownership developed |  |  |
|  | Sub-Total |  | 111,700 |  |  |  |  |
| Key Service Area: 000039 Policies, Regulations and Standards PIAP Output: 06511101 NRECCLWM programme Policy frameworks developed/reviewed | Land related laws (Land Act, Land regulations and guidelines, RTA, Surveyors Act, Surveyor Registration Act) reviewed | N/A |  |  | Land regulations finalized and submitted to first parliamentary council |  |  |
|  | ADR guidelines on settling disputes on Customary land and other land tenures validated and disseminated in the 4 regions. | ADR guidelines on settling disputes on Customary land and other land tenures validated and disseminated in 5 districts in Northern region. |  |  | ADR Guidelines disseminated in 5 districts of Oyam, Gulu, Lira, Nwoya and Amuru |  |  |
|  | Revised National Land Policy,2025 disseminated | - 2 meetings to validate the revised National Land Policy , 2025 held |  |  | 2 meetings held to discuss the National Land Policy |  |  |
|  | Land related laws, policies, and guidelines disseminated in 50 District Local governments. | Land related laws, policies, and guidelines disseminated in 12 District Local governments. |  |  | Guidelines for inspection and evictions disseminated in 24 districts of Jinja,Luuka, Kamuli, Iganga, Mayuge, Kaliro, Bugiri, Namayingo, Busia, Tororo, Butaleja, Budaka, Kibuku, Pallisa, Mbale, Namisindwa, Sironko, Bulambuli, Kapchorwa, Bukwo, Kumi, Bukedea, Serere, Soroti |  |  |
| Sub-Total |  |  | 98,025 |  |  |  |  |
|  | Total |  | 209,725 | 209,725 |  |  |  |

Name:										Signature:					Date:

Head of Department/Project Coordinator/MZO Head

Attach signed departmental minutes