MINISTRY OF LANDS, HOUSING AND URBAN DEVELOPMENT
QUARTER ONE PERFORMANCE REPORT FOR FY 2026/2027
Department: Land Administration 
	PIAP output 
	Annual Output 
	Planned Q1 Target   
	Approved Q1 Budget (UGX)
	Q1 Warrants (UGX)
	Achieved Q1 physical performance
	Amount spent (UGX)
	Reasons for Variation 

	Key Service Area: 000078 Land Management

PIAP OUTPUT:  10030101 Land management infrastructure enhanced 


	500 Land Management institutions trained in land management.
	125 Land Management institutions in Eastern region trained in land management
	
	
	121 Land Management institutions trained; 25 DLBs, DLOs, 96 ALCs and Recorders in Jinja,Luuka, Kamuli, Iganga, Mayuge, Kaliro, Bugiri, Namayingo, Busia, Tororo, Butaleja, Budaka, Kibuku, Pallisa, Mbale, Namisindwa, Sironko, Bulambuli, Kapchorwa, Bukwo, Kumi, Bukedea, Serere, Soroti
	
	…

	
	-100 Land Management institutions supervised and inspected
	-25 Land Management institutions in Eastern region supervised and inspected 
	
	
	20 Land Management institutions supervised and inspected; 5 DLBs and 15 ALCs and Recorders Supervised and inspected land management institutions in Bugweri, Buyende, Kapelebyong, Katakwi, Amuria
	
	

	
	-50 DLBs vetted and approved 
	 -12 DLBs vetted and approved 
	
	
	
7 DLBs vetted; 1 DLB (Rubanda) approved, 6 DLBs (Mubende, Kabarole, Amuria, Hoima, Maracha, Mityana) pending approval.
	
	

	
	-40 Land Dispute redress Committees in 40 Districts trained in ADR mechanisms. 

	-10 Land Dispute redress Committees in 10 Districts in Northern Uganda trained in ADR mechanisms 

	
	
	10 Land Dispute Redress Committees in Pakwach, Zombo, Maracha, Koboko, Yumbe, Obongi, Moyo, Adjumani districts trained. 
	
	

	
	-Membership dues to Uganda Law society and East African Law society paid. 

	N/A
	
	
	N/A
	
	

	
	-80 land disputes investigated and reports prepared. 

	 -20 land disputes investigated and reports prepared. 

	
	
	35 land Disputes and complaints handled/ investigated and 15 pending final reports


	
	

	
	-Capacities of departmental staff enhanced in ADR in land management and best practices. 

	N/A
	
	
	N/A
	
	

	
	 -22 MZOs in Central, Western, Northern and Eastern regions monitored and inspected. 


	 
-03 MZOs in Northern region monitored and inspected. 

	
	
	3 MZOs of Gulu, Arua, & Lira monitored and inspected to assess whether the MZOs are carrying out their statutory land administration and management responsibilities effectively, efficiently and in line with applicable laws, policies and procedures. 
	
	

	
	-80 land transactions inspected for compliance with established legal and administrative standards. 

	 -20 land transactions inspected for compliance with established legal and administrative standards. 


	
	
	20 Land transactions inspected for compliance with established legal and administrative standards in the districts of Lamwo, Mubende, Lwengo , Kyotera and Wakiso
	
	

	
	 
-Local leaders and mediators in 40 Districts trained land dispute resolution. 

	-Local leaders and mediators in 10 Districts in Northern region trained land dispute resolution 

	
	
	Trained local leaders and mediators in 12 districts Oyam, Lira, Gulu, Omoro, Nwoya, Amuru, Pader, Agago, Kitgum, Lamwo, Terego, Arua
	
	

	
	- Study on the effect of Certificates Of Occupancy on Mailo Land undertaken and report produced. 

	Procurement of consultant 

	
	
	TORs for the consultant to undertake the Study on the effect of Certificates of Occupancy on Mailo Land developed.
	
	

	
	- Study undertaken on post issuance transactions for Certificates of Customary Ownerships and report produced 

	Procurement of consultant 

	
	
	TORs for the consultant to undertake the study on post issuance transactions for Certificates of Customary Ownership developed

	
	

	
	Sub-Total
	
	111,700
	
	
	
	

	
Key Service Area: 000039 Policies, Regulations and Standards


PIAP Output: 06511101 NRECCLWM programme Policy frameworks developed/reviewed
	Land related laws (Land Act, Land regulations and guidelines, RTA, Surveyors Act, Surveyor Registration Act) reviewed 

	N/A
	
	
	Land regulations finalized and submitted to first parliamentary council
	
	

	
	ADR guidelines on settling disputes on Customary land and other land tenures validated and disseminated in the 4 regions. 

	ADR guidelines on settling disputes on Customary land and other land tenures validated and disseminated in 5 districts in Northern region. 

	
	
	ADR Guidelines disseminated in 5 districts of Oyam, Gulu, Lira, Nwoya and Amuru
	
	

	
	Revised National Land Policy,2025 disseminated 

	- 2 meetings to validate the revised National Land Policy , 2025 held 

	
	
	2 meetings held to discuss the National Land Policy
	
	

	
	Land related laws, policies, and guidelines disseminated in 50 District Local governments. 

	Land related laws, policies, and guidelines disseminated in 12 District Local governments. 

	
	
	Guidelines for inspection and evictions disseminated in 24 districts of Jinja,Luuka, Kamuli, Iganga, Mayuge, Kaliro, Bugiri, Namayingo, Busia, Tororo, Butaleja, Budaka, Kibuku, Pallisa, Mbale, Namisindwa, Sironko, Bulambuli, Kapchorwa, Bukwo, Kumi, Bukedea, Serere, Soroti
	
	

	Sub-Total
	
	
	98,025
	
	
	
	

	
	Total 
	
	209,725
	209,725
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