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MINISTRY OF LANDS, HOUSING AND URBAN DEVELOPMENT
QUARTER ONE PERFORMANCE REPORT FOR FY 2026/2027

Department: MINISTRY ZONAL OFFICES-  MBARARA MZO
	[bookmark: _Hlk242254448]KEY SERVICE AREA/PIAP output
	Annual Output 
	Planned Q1 Target   
	Approved budget
	Warrants
	
	Achieved Q1 physical performance
	Amount Spent
	Reasons for Variation 

	Key Service Area: 000039 Policies, Regulations and Standards; PIAP Output 10511201 Policy and Legal Framework developed, reviewed, and implemented (PAS)
	04 Barazas organized at the MZOs on land management issues. and to sensitize the public on Ministry services
	01 Baraza organized at the MZOs on land management issues. and to sensitize the public on Ministry services
	
	
	
	
	…
	…

	
	04 Locus visits and boundary opening undertaken within the MZOs’ jurisdictions
	01 Locus visit and boundary opening undertaken within the MZOs’ jurisdictions
	10,008,576,
	10,008,576
	
	Locus visits to Nyabusozi, Kiruhura ,and Ruhama Ntungamo conducted

SLAAC Titles distributed in Isingiro and Ibanda Districts
	4,003,431



5,337,907
	

	
	Capacity building of 08 MZO staff undertaken in various fields.
	Capacity building of 02 MZO staff undertaken in various fields.
	
	
	
	
	
	

	
	04 Annual subscriptions made to professional bodies
	01 Annual subscription made to a professional body
	
	
	
	
	
	

	
	Minor civil repairs of the MZO structures undertaken
	01 office block painted (administration block)
	14,679,245
	14,679,245
	
	Plumbing and drainage works undertaken

Broken glasses, doors and Electric appliances
	4,104,019


7,179,384
	

	
	Annual Revenue Generated within the MZO's jurisdiction
	Q1 revenue of UGX 473,000,000 collected
	
	
	
	
	
	

	
	04 radio talk shows held on Land Management
	01 radio talk show held on Land Management
	5,337,907
	5,337,907
	
	Radio talk show conducted
	5,337,997
	

	
	National Land Valuation Management Information System (N-LaVMIS) managed
	01 Training session and rolling out of N-LaVMIS undertaken 
	
	
	
	
	
	

	
	04 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken
	01 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken
	
	
	
	
	
	

	
	12 Court cases litigated
	03 Court cases litigated
	
	
	
	
	
	

	
	20,000 titles produced and issued, including SLAAC
	5,000 titles produced and issued, including SLAAC
	
	
	
	
	
	

	
	MZO equipment serviced and maintained, including computers, printers and scanners
	MZO office equipment (computers) serviced
	
	
	
	
	
	

	
	MZO Vehicles serviced and maintained
	02 MZO Vehicles serviced and maintained
	6,672,384
	6,672,384
	
	Motor vehicle repaired
	6,672,384
	

	
	Staff team-building, health and wellness activities conducted
	01 staff team-building and wellness sessions conducted
	
	
	
	
	
	

	
	Gender, HIV/AIDS, environment and other crosscutting issues mainstreamed
	100 condoms supplied to staff

02 awareness activities conducted 
	
	
	
	
	
	

	
	01 Land awareness week conducted 
	05 Stakeholder engagements conducted
	
	
	
	
	
	

	
	Finance Committee Meetings facilitated
	01 Finance Committee Meetings facilitated
	
	
	
	
	
	

	
	Workshops, meetings and seminars
	Staff welfare provided
	16, 680,961
	16, 680,961
	
	Staff welfare provided
	5,000,000
	Topped up for staff allowances

	
	04 Quarterly releases for fuel , lubricants and oils
	01 quarterly release for fuel
	10,675,814
	10,675,814
	
	Fuel for generator and staff provided
	10,670,000
	

	
	Staff allowances
	
	5,337,907
	5,337,907
	
	
	
	

	
	Staff training
	
	4,003,431
	4,003,431
	
	
	
	Topped up on Staff allowanes

	
	Sub-Total
	
	73,396,226
	73,396,226
	
	
	48,305,122
	

	
	Total 
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