MINISTRY OF LANDS, HOUSING AND URBAN DEVELOPMENT

QUARTER ONE PERFORMANCE REPORT FOR FY 2026/2027

Department: MINISTRY ZONAL OFFICES

| KEY SERVICE AREA/PIAP output | Annual Output | Plan ned Q1 Target | Approved budget | Warrants |  | Achieved Q1 physical performance | Amount Spent | Reasons for Variation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Key Service Area: 000039 Policies, Regulations and Standards; PIAP Output 10511201 Policy and Legal Framework developed, reviewed, and implemented (PAS) | 04 Barazas organized at the MZOs on land management issues. and to sensitize the public on Ministry services | 01 Baraza organized at the MZOs on land management issues. and to sensitize the public on Ministry services | 6,240,000 | 6,240,000 |  | Community Barraza held at MZO on the land management issues and sensitized the public on ministry services | 6,240,000 | NIL |
|  | 04 Locus visits and boundary opening undertaken within the MZOs’ jurisdictions | 01 Locus visit and boundary opening undertaken within the MZOs’ jurisdictions |  |  |  |  | Nil |  |
|  | Capacity building of 08 MZO staff undertaken in various fields. | Capacity building of 02 MZO staff undertaken in various fields. | 3,077,187 | 3,071,000 |  | Capacity building of Mzo staff on the standards of service delivery in ministry of Lands | 3,071,000 | None |
|  | 04 Annual subscriptions made to professional bodies | 01 Annual subscription made to a professional body | 400,000 | Nil |  | Annual subscription made to professional body (PAAU) |  | Payments not made. |
|  | Minor civil repairs of the MZO structures undertaken | 01 office block painted (administration block) | 11,283,019 | 11,282,000 |  | 01 office repairs done lighting, plumbing and minor internal repairs and welding of all metallic doors and gate. | 11,282,000 | None |
|  | Annual Revenue Generated within the MZO's jurisdiction | Q1 revenue of UGX 473,000,000 collected |  |  |  |  |  |  |
|  | 04 radio talk shows held on Land Management | 01 radio talk show held on Land Management | 340,000 | 340,000 |  | One radio talk show held | 340,000 |  |
|  | National Land Valuation Management Information System (N-LaVMIS) managed | 01 Training session and rolling out of N-LaVMIS undertaken |  |  |  |  |  |  |
|  | 3 Mediation and Alternative Dispute Resolution (ADR) activities undertaken | 02 Mediation and Alternative Dispute Resolution (ADR) activities undertaken a per complain submitted to our office | 7,421,000 | 3, 313,100 |  | Two done with communities of kakoriyang farmers cooperate and an individual Odeke and Orebere community land association | 3,313,100 | 4,107,900 Not funded |
|  | 12 Court cases litigated | 03 Court cases litigated |  |  |  | Two cases submitted to state Attorney | NIL | Nil |
|  | 20,000 titles produced and issued, including SLAAC | 5,000 titles produced and issued, including SLAAC |  |  |  |  |  |  |
|  | MZO equipment serviced and maintained, including computers, printers and scanners | MZO office equipment (computers) serviced |  |  |  |  |  |  |
|  | MZO Vehicles serviced and maintained | 02 MZO Vehicles serviced and maintained | 5,128,645 | 5,120,000 |  | One vehicle repaired and its functional | 5,120,000 | Nil |
|  | Staff team-building, health and wellness activities conducted | 01 staff team-building and wellness sessions conducted |  |  |  |  |  |  |
|  | Gender, HIV/AIDS, environment and other crosscutting issues mainstreamed | 100 condoms supplied to staff 02 awareness activities conducted |  |  |  |  |  |  |
|  | 01 Land awareness week conducted | 05 Stakeholder engagements conducted |  |  |  |  |  |  |
|  | Finance Committee Meetings facilitated and other mandatory meetings facilitated | 01 Finance Committee Meetings facilitated One staff meeting Induction of | 7,720,000 | Nil |  | One finance meeting attended, 1 staff meeting, induction of ministers, administrator meeting attended. | Nil | Not facilitated |
|  | Familiarization visit to districts | 3 familiarization visit | 4,135,000 | 3,475,000 |  | Three familiarization visits done | 3,475,000 | 660,000 not funded |
|  | Fuel lubricants and oils | One generator and one vehicle | 8,205, 832 | 8,205,832 |  | Fuel ,lubricants and oils purchased | 8,205,832 |  |
|  | Welfare for staff | Welfare for staff | 1,680,000 | 1,680,000 |  | Welfare provided for staff | 1,680,000 | None |
|  | Sub-Total | Proposed planned planned for warranting | 73,000,000 55,630,683 | 53,000,000 42,726,932 |  |  | 42,726,932 |  |
|  | Total |  | Deficit 17,369,317 | Deficit 10,273,068 |  |  |  |  |

Name:										Signature:					Date:

Head of Department/Project Coordinator/MZO Head

PROPOSED QUARTER TWO ACTIVITIES 2026/2027 FY MOROTO MZO

| s/n | Activities | Department | Cost |
| --- | --- | --- | --- |
|  | community Barraza in the south district of karamoja | All departments |  |
|  | Gender, HIV/AIDS, Environment and other crosscutting issues | Finance and administration |  |
|  | Staff team-building, health and wellness activities conducted | Finance and administration |  |
|  | Sensitization of the 9 districts on the lavims system and management | Land reforms |  |
|  | Locus visit by the registrar of titles | Land registration |  |
|  | mediation meeting on the conflicted areas submitted to the mzo | Land registration |  |
|  | Mzo vehicles serviced and maintained | Finance and administration |  |
|  | Welfare for staff | Finance and administration |  |
|  | External repair of the office building and beautification with ornamentals | Finance and administration |  |
|  | annual subscriptions made to professional bodies | Administration and finance |  |
|  | Travel for APAAM round table meeting and other mandatory meetings at headquarters (performance review meetings, finance meeting, general staff meeting) and any other meeting. | Administration and finance and all other departments |  |
|  | Backstopping support to district land boards, physical planning committee of 4 district. | Land reform |  |
|  | Locus visits and boundary opening undertaken within the mzos’ jurisdictions | Surveys and mapping |  |
|  | Fuel ,,oils and lubricants | F/A |  |
|  | Consolidated allowances for staff | Selected non enhanced staff. |  |

Attach signed departmental minutes