MINISTRY OF LANDS, HOUSING AND URBAN DEVELOPMENT

QUARTER ONE PERFORMANCE REPORT FOR FY 2026/2027

Department: MINISTRY ZONAL OFFICES-  MPIGI MZO

| KEY SERVICE AREA/PIAP output | Annual Output | Planned Q1 Target | Approved budget | Warrants |  | Achieved Q1 physical performance | Amount Spent | Reasons for Variation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Key Service Area: 000039 Policies, Regulations and Standards; PIAP Output 10511201 Policy and Legal Framework developed, reviewed, and implemented (PAS) | 04 Barazas organized at the MZOs on land management issues. and to sensitize the public on Ministry services | 01 Baraza organized at the MZOs on land management issues. and to sensitize the public on Ministry services |  |  |  |  | … | … |
|  | 04 Locus visits and boundary opening undertaken within the MZOs’ jurisdictions | 01 Locus visit and boundary opening undertaken within the MZOs’ jurisdictions |  |  |  |  |  |  |
|  | Capacity building of 08 MZO staff undertaken in various fields. | Capacity building of 02 MZO staff undertaken in various fields. |  |  |  |  |  |  |
|  | 04 Annual subscriptions made to professional bodies | 01 Annual subscription made to a professional body |  |  |  |  |  |  |
|  | Minor civil repairs of the MZO structures undertaken | 01 office block painted (administration block) | 14,679,245 | 14,679,245 |  | Unblocking of toilets and tank cleaning Emptying of the sewer/septic tank Broken glasses, doors locks Fumigation Repair of the signpost Repair of toilets | 860,000 2,300,000 1,700,000 5,183,000 690,000 550,000 | Processing was based on IPF for small MZOs |
|  | Annual Revenue Generated within the MZO's jurisdiction | Q1 revenue of UGX 473,000,000 collected |  |  |  |  |  |  |
|  | 04 radio talk shows held on Land Management | 01 radio talk show held on Land Management | 5,337,907 | 5,337,907 |  |  | 00 | Not honoured |
|  | National Land Valuation Management Information System (N-LaVMIS) managed | 01 Training session and rolling out of N-LaVMIS undertaken |  |  |  |  |  |  |
|  | 04 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken | 01 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken |  |  |  |  |  |  |
|  | 12 Court cases litigated | 03 Court cases litigated |  |  |  |  |  |  |
|  | 20,000 titles produced and issued, including SLAAC | 5,000 titles produced and issued, including SLAAC |  |  |  |  |  |  |
|  | MZO equipment serviced and maintained, including computers, printers and scanners | MZO office equipment (computers) serviced |  |  |  |  |  |  |
|  | MZO Vehicles serviced and maintained | 02 MZO Vehicles serviced and maintained | 6,672,384 | 6,672,384 |  | Motor vehicle repaired Motor vehicle tyres provided | 1,942, 693 3,186,000 | Insufficient funds Processing was based on IPF for small MZOs |
|  | Staff team-building, health and wellness activities conducted | 01 staff team-building and wellness sessions conducted |  |  |  |  |  |  |
|  | Gender, HIV/AIDS, environment and other crosscutting issues mainstreamed | 100 condoms supplied to staff 02 awareness activities conducted |  |  |  |  |  |  |
|  | 01 Land awareness week conducted | 05 Stakeholder engagements conducted |  |  |  |  |  |  |
|  | Finance Committee Meetings facilitated | 01 Finance Committee Meetings facilitated |  |  |  |  |  |  |
|  | Workshops, meetings and seminars | Office welfare provided 01 Seminar attended | 16,680,960 | 16, 680,961 |  | 6th Administrative officers’ Forum in Gulu attended Office welfare provided | 2,940,000 4,420,000 | Balance was meant for a Baraza but was not honoured |
|  | 04 Quarterly releases for fuel , lubricants and oils | 01 quarterly release for fuel | 10,675,815 | 10,675,815 |  | Fuel for generator and staff provided | 10,675,815 | Fully released |
|  | Travel inland | Travel in land made | 10,008,576 | 10,008,576 |  | Three meetings were attended by PAS at Headquarters | 2,325,000 | Balance was meant for an activity for the Surveying Section but was not honoured |
|  | Allowances | Allowances to staff whose salaries were not enhanced and non-scientists paid | 5,337,907 | 5,337,907 |  |  | 13,662,000 | Shortfall was covered using other items |
|  | Staff training |  | 4,003,430 |  |  |  |  |  |
|  | Sub-Total |  | 73,396,200 | 50,434508 |  |  | 50,434,508 | 22,961,692 was not spent due to the obbservations herein |
|  | Total |  | 73,396,200 | 50,434508 |  |  | 50,434508 |  |

Name:										Signature:					Date:

Head of Department/Project Coordinator/MZO Head

Attach signed departmental minutes