MINISTRY OF LANDS, HOUSING AND URBAN DEVELOPMENT

QUARTER ONE PERFORMANCE REPORT FOR FY 2026/2027

Department: MITYANA MINISTRY ZONAL OFFICES

| KEY SERVICE AREA/PIAP output | Annual Output | Planned Q1 Target | Approved budget | Warrants |  | Achieved Q1 physical performance | Amount Spent | Reasons for Variation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Key Service Area: 000039 Policies, Regulations and Standards; PIAP Output 10511201 Policy and Legal Framework developed, reviewed, and implemented (PAS) | 04Barazas organized at the MZOs on land management issues. and to sensitize the public on Ministry services | 01Baraza organized at the MZOs on land management issues. and to sensitize the public on Ministry services 9in Kalangalo and Bulera subcounties-Mityana District | 12,821,612 | 23,515,000 |  | All achieved | 23,515,000 | We had some meetings more planned for because of the directives from the Minister to carryout locus visits. |
|  | 04 Locus visits and boundary opening undertaken within the MZOs’ jurisdictions | 01 Locus visit and boundary opening undertaken within the MZOs’ jurisdictions | 8,000,000 | 8,000,000 |  | All achieved | 8,000,000 |  |
|  | Capacity building of 08 MZO staff undertaken in various fields. | Capacity building of 02 MZO staff undertaken in various fields. Gulu workshop) Travel inlands | 4,474,000 | 4,474,000 |  | All achieved | 4,474,000 |  |
|  | 04 Annual subscriptions made to professional bodies | 01Annual subscription made to a professional body | - | - |  | - | - |  |
|  | Minor civil repairs of the MZO structures undertaken | 01 office block painted(administration block) | - | - |  | - | - |  |
|  | Annual Revenue Generated within the MZO's jurisdiction | Q1 revenue of UGX 473,000,000 collected |  |  |  |  |  |  |
|  | 04 radio talk shows held on Land Management | 01radio talk show held on Land Management | 4,102,916 | 4,102,916 |  |  | 4,102,916 |  |
|  | National Land Valuation Management Information System (N-LaVMIS) managed | 01 Training session and rolling out of N-LaVMIS undertaken |  |  |  |  |  |  |
|  | 04 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken | 01 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken |  |  |  |  |  |  |
|  | 12 Court cases litigated | 03 Court cases litigated |  |  |  |  |  |  |
|  | 20,000 titles produced and issued, including SLAAC | 5,000 titles produced and issued, including SLAAC | - |  |  |  |  |  |
|  | MZO equipment serviced and maintained, including computers, printers and scanners | MZO office equipment (computers) serviced (Faulty lights replaced) | 5,128,645 | 2,625,000 |  |  | 2,65,000 |  |
|  | MZO Vehicles serviced and maintained | 02 MZO Vehicles serviced and maintained | ,, |  |  |  |  |  |
|  | Staff team-building, health and wellness activities conducted | 01 staff team-building and wellness sessions conducted | 11,283,01 |  |  |  |  |  |
|  | Gender, HIV/AIDS, environment and other crosscutting issues mainstreamed | 100 condoms supplied to staff 02 awareness activities conducted | ,, |  |  |  |  |  |
|  | 01 Land awareness week conducted | 05 Stakeholder engagements conducted | ,, |  |  |  |  |  |
|  | Finance Committee Meetings facilitated | 01 Finance Committee Meetings facilitate (general staff meeting held at presidents conference hall) | 4,102,916 | 2,435,000 |  |  | 2,435,000 |  |
|  | Sub-Total |  | 56,415,094 |  |  |  | 37,976,916 |  |
|  | Total | 225,660, 376 |  |  |  |  |  |  |

Name:		Dr Ivan Lwanyaga								Signature:  Date:	12th October, 2026

Head of Department/Project Coordinator/MZO Head

Attach signed departmental minutes