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MINISTRY OF LANDS, HOUSING AND URBAN DEVELOPMENT
QUARTER ONE PERFORMANCE REPORT FOR FY 2026/2027

Department: MITYANA MINISTRY ZONAL OFFICES 
	[bookmark: _Hlk242254448]KEY SERVICE AREA/PIAP output
	Annual Output 
	Planned Q1 Target   
	Approved budget
	Warrants
	
	Achieved Q1 physical performance
	Amount Spent
	Reasons for Variation 

	Key Service Area: 000039 Policies, Regulations and Standards; PIAP Output 10511201 Policy and Legal Framework developed, reviewed, and implemented (PAS)
	04Barazas organized at the MZOs on land management issues. and to sensitize the public on Ministry services
	01Baraza organized at the MZOs on land management issues. and to sensitize the public on Ministry services
9in Kalangalo and Bulera subcounties-Mityana District
	12,821,612
	23,515,000
	
	All achieved 
	23,515,000
	We had some meetings more planned for because of the directives from the Minister to carryout locus visits.

	
	04 Locus visits and boundary opening undertaken within the MZOs’ jurisdictions
	01 Locus visit and boundary opening undertaken within the MZOs’ jurisdictions
	8,000,000
	8,000,000
	
	All achieved
	8,000,000
	

	
	Capacity building of 08 MZO staff undertaken in various fields.
	Capacity building of 02 MZO staff undertaken in various fields. Gulu workshop)
Travel inlands
	4,474,000
	4,474,000
	
	All achieved
	4,474,000
	

	
	04 Annual subscriptions made to professional bodies
	01Annual subscription made to a professional body
	-
	-
	
	-
	-
	

	
	Minor civil repairs of the MZO structures undertaken
	01 office block painted(administration block)
	-
	-
	
	-
	-
	

	
	Annual Revenue Generated within the MZO's jurisdiction
	Q1 revenue of UGX 473,000,000 collected
	
	
	
	
	
	

	
	04 radio talk shows held on Land Management
	01radio talk show held on Land Management
	4,102,916
	4,102,916
	
	
	4,102,916
	

	
	National Land Valuation Management Information System (N-LaVMIS) managed
	01 Training session and rolling out of N-LaVMIS undertaken
	
	
	
	
	
	

	
	04 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken
	01 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken
	
	
	
	
	
	

	
	12 Court cases litigated
	03 Court cases litigated
	
	
	
	
	
	

	
	20,000 titles produced and issued, including SLAAC
	5,000 titles produced and issued, including SLAAC
	-
	
	
	
	
	

	
	MZO equipment serviced and maintained, including computers, printers and scanners
	MZO office equipment (computers) serviced
(Faulty lights replaced)
	5,128,645
	2,625,000
	
	
	2,65,000
	

	
	MZO Vehicles serviced and maintained
	02 MZO Vehicles serviced and maintained
	,,
	
	
	
	
	

	
	Staff team-building, health and wellness activities conducted
	01 staff team-building and wellness sessions conducted
	11,283,01
	
	
	
	
	

	
	Gender, HIV/AIDS, environment and other crosscutting issues mainstreamed
	100 condoms supplied to staff

02 awareness activities conducted 
	,,
	
	
	
	
	

	
	01 Land awareness week conducted 
	05 Stakeholder engagements conducted
	,,
	
	
	
	
	

	
	Finance Committee Meetings facilitated
	01 Finance Committee Meetings facilitate
(general staff meeting held at presidents conference hall)
	4,102,916
	2,435,000
	
	
	2,435,000
	

	
	
	
	
	
	
	
	
	

	
	Sub-Total
	
	56,415,094
	
	
	
	37,976,916
	

	
	Total 
	225,660, 376
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