## F&A Q1 Performance (2)
Department/PIAP Output
Annual Activity
PIAP Output 06511101 Policy frameworks developed/reviewed | 3 stakeholders engagements carried out on Survey and Mapping Bill, Survey Reports standards and National Mapping Standards developed

## F&A Q1 Performance
Q1 PERFORMANCE REPORTING TEMPLATE FOR VOTE FUNCTION: 04 POLICY, PLANNING AND SUPPORT SERVICES
Division/Service Area/PIAP output | ANNUAL ACTIVITY |  | Q1 PLANNED ACTIVITIES |  | ACTUAL PERFORMANCE |  |  | Plann edQ2
|  |  | Activity | Budget | Activity | Warrant | Comment | Activities | warrant
Key Service Area: 000010 Leadership and Management; PIAP Output 10511607 Leadership and Management coordinated ( PAS) | 12 Senior Management meetings held |  | 3 Senior Management meetings held
| 4 International Obligations and conferences attended |  | 1 International Obligations and conferences started
| -Responses to Cabinet issues prepared and presented |  | Responses to Cabinet issues prepared prepared
| -12 Top/ Policy Management meetings held |  | 2 Political oversight exercises undertaken
| -8 Political oversight exercises undertaken and Reports produced |  | 2 Political oversight exercises undertaken and Reports produced
Budget |  | 2202400 |  | 525600 |  | 525600 |  |  | 525600
Key Service Area: 000011 Communication and Public Relations;PIAP Output 10511606 Communication and Public Relations strengthened ( Senior Information Officer) | 8 Barazas/open days organized to sensitize the public on Ministry services, profile complaints, responses and grievances in all four regions of the country |  | 2 Barazas/open days organized to sensitize the public on Ministry services,profile complaints, responses andgrievances in 2 Districts in Eastern Region i.e Tororo and Mbale
| Ministry website Upgraded and Maintained. |  | Ministry website Upgraded and mantained
| 6000 Information requests responded to from both men and women |  | 1500 Information requests from both men and women responded to.
| Communications equipment; cameras, ICT maintained and serviced |  | Communications equipment; cameras, ICT mantained and serviced
| Subscription for Tidio, Twitter Blue, Sucuri and wordfence paid |  | Subscription for Tidio andTwitter Blue paid
| Ministry IEC material i.e access to information manual, Client charter, Land procedures developed, printed and disseminated |  | Ministry IEC material i.e access to information manual, client charter land procedures developed, printed disseminated
competencies of 4 Communications Division staff strengthened in public relations, crisis communication and Dissemination
| Targeted ministry Adverts and communications designed and placed. |  | Targeted ministry Adverts and communications designed and placed
| Ministry IEC material translated to Local languages and disseminated |  | Ministry IEC material translated to Luganda, and Ateso and disseminated during the open days
Annual total | 400000 |  | Quarter one | 98000
Key Service Area: 000013 HIV/AIDS Mainstreaming;PIAP Output 10511604 Cross cutting issues mainstreamed ( TBD) | 4 HIV/AIDs/Malaria/Tuberculosis committee meetings held |  | 1 HIV/AIDs/Malaria/Tuberculosis Committee meeting held
| Condoms procured quarterly for all 26 Staff structures (22 Ministry Zonal Offices, Head quarters and the National Land Information Center ) |  | condoms procured and maintained for all 26 staff structures
2 Voluntary Counselling and Testing exercises undertaken for staff
| Condom dispensers procured and placed in all washrooms at both Headquarters and Ministry Zonal Offices |  | Condom dispensers procured and placed in all washrooms at both Ministry and Zonal offices
| Quarterly HIV /AIDS, Malaria and Tuberculosis sensitization exercises undertaken |  | Q1 HIV /AIDS, Malaria and Tuberculosis sensitisation exercise undertaken
Annual total | 100000 |  | Quarter One | 20000
Key Service Area: 000014 Administrative and Support Services; PIAP Output 10511101 Enhanced coordination and programme secretariat services (PAS) | 12 months Guard and security services provided for the Ministry headquarters and the National Land Information center |  | 3 months Guard and security services provided for the Ministry headquarters and the national land Information Center
| -Property Management / Cleaning services provided for all Ministry offices |  | Property Management / Cleaning services provided for all ministry
| Annual Ministry property rates paid |  | Quarter 1 Ministry property rates paid
Computer Soft wares and Anti viruses procured
| 171 MVs serviced and maintained |  | 171 MVs serviced and maintained
| Ugx 25bn paid as compensation to ranchers and third parties |  | Compensation paid to ranchers and third parties
| 50 transport equipment installed with New Security Enhanced Digital Number Plates |  | 10 transport equipment installed with
| Annual Utility Bills paid |  | Quarter 1 Utility Bills paid
| Minor repairs on civil works undertaken quarterly |  | Minor repairs on civil works undertaken in quarter 1
| All Ministry fleet maintained and serviced regularly |  | All Ministry fleet maintained and serviced regularly
Annual total | 29250000 |  | quarter One | 1055000
Key Service Area: 000027 Programme Working Group Secretariat Service; PIAP Output 10511101 Enhanced coordination and programme secretariat services (AC/Planning) | 2 SUHP Programme Planning and Budgeting meetings held.
| -Quarterly programme-level planning and budgeting meetings held |  | Quarterly programme-level planning and budgeting meetings held
-Programme vote allocations for FY 2027/28 approved and submitted to MoFPED
-1 Sustainable Urbanization and Housing Programme Leadership meeting held
- Capacity building of staff in Programme budgeting incorporating climate and Gender specific issues conducted.
| Technical support to Leadership Committee, PWG and TWG provided |  | Technical support to Leadership committee, PWG and TWG provided
Inter-ministerial and inter-agency budget allocations coordinated in line with programme priorities, transparency and accountability requirements
Annual Budget | 600000 |  | Quarter One Budget | 180000
Key Service Area: 000039 Policies, Regulations and Standards; PIAP Output 10511201 Policy and Legal Framework developed, reviewed, and implemented (AC/Policy) | Policy review meetings workshops facilitated
| Domestic field trips for data collection or consultations on policy issues undertaken in 5 districts in each of the 4 regions in the country |  | 1 Domestic field trip for data collection or consultations on policy issues undertaken in 5 districts in the eastern region
| 1 Cabinet Forward Agenda developed |  | 1 Cabinet Forward Agenda developed
| 12 Cabinet Memoranda prepared and submitted to Cabinet |  | 3 Cabinet Memoranda prepared and submited to Cabinet
Ministerial Policy Statement FY 2027/28 prepared and submitted to Parliament by 15th March 2027
| 5 Policy briefs and position papers on topical Public Policy issues prepared |  | 1 Policy brief and position paper on topical public policy issues prepared
capacity of 7 staff strengthened in policy analysis
| 4 research/study reports on sectoral policy issues prepared |  | 1 research/study report on sectoral policy issues prepared
3 Regulatory Impact Assessment Reports prepared
Annual Budget | 400000 |  | Quarter One Budget | 77500
Key Service Area: 000040 Inventory Management; PIAP Output 10511610 Efficient Records management (Senior Inventory Officer) | -Periodic Assessment exercises of receipt, storage and inventory accountability undertaken in the 22 Ministry Zonal Offices |  | Quarterly stock taking exercise conducted & amp; report produced
| -Fixed Asset Register maintained and Updated |  | Fixed Asset Management verification exercise conducted for Head office and 5 MZOs
| Staff of 22 MZOs trained on compliance to Asset Management procedures |  | Staff of 5 MZOs trained on compliance to asset management procedures
Bi-Annual Asset identification and engraving conducted.
Capacity of 2 staff enhanced in Inventory management courses
Annual Budget | 350000 |  | Quarter One Budget | 77800
Key Service Area: 000051 Affiliated and professional Bodies; PIAP Output 10511604 Cross cutting issues mainstreamed (PAS) | Budget support to Surveyors Registration Board provided |  | Budget support to Surveyors Registration Board provided
| -Budget support to Institute of Surveys and Land Management provided |  | Budget support to Institute of Surveys and land management provided
Subscription to Regional Centre for Mapping of Resources for Development (RCMRD) paid
Annual Budget | 516616 |  | Quarter One Budget | 129154
Key Service Area: 000089 Climate Change Mitigation;PIAP Output 10511604 Cross cutting issues mainstreamed (TBD) | Climate resilience integrated into the Urban Transport strategy |  | 2 stakeholder engagements undertaken to review urban transport startegy
|  |  | Sub total | 25000
annual Budget | 100000 |  | Quarter One Budget | 25000
Key Service Area: 080012 Project Management Services; PIAP Output 10511101 Enhanced coordination and programme secretariat services (AC/Planning) |  |  | Technical support provided to 12 Departments in development of bankable projects
1 Project Preparation Committee (PPC) meetings held
Q1 performance reports for Ministry projects prepared
|  |  | Sub total | 129809
Grand total

## Sheet1
NDPIV OBJECTIVE | PIAP RESULT | Key output | Activity | Activity Cost | Source of Funding
Develop and maintain Urban Infrastructure in line with Physical Development Plans | Improved urban infrastructure | Detailed Physical Development Plans developed for respective local governments | Identify, prioritise and conduct stakeholder consultations and community sensitization on detailed physical development planning in LGs
Support Preparation of detailed land-use, zoning and development-control plans and draft detailed Physical Development Plans (DPDPs) for selected LGs
Support Processing of plans for approval by the relevant planning authorities.
Support implementation and enforcement of the approved plans
Monitor compliance and periodically review/update the Detailed Physical Development Plans
| Increased compliance with land use in urban areas | Urban Councils Complying to Land Use Regulatory Framework | Identify and Sensitize communities and developers on land-use regulations.
Train physical planners and development-control personnel.
Provide technical support and backstopping to Local Governments.
Conduct field inspections and compliance assessments.
Prepare and submit compliance reports
Enforce adherence to approved physical development plans.
Disseminate physical planning standards and guidelines.
City/Municipal/Town Council physical development plans developed/implemented.
Detailed physical development plans developed for selected cities and local governments.
Cities/Municipalities/ Town councils compliance with physical planning guidelines andstandards and approved physical development plans.
Develop sustainable waste management systems | Improved livability and cleanliness of urban areas |  | Waste management systems established | Develop and enforce the Waste Management Policy.
|  |  | Air quality improved | Develop and implement municipal and citywide waste master plans.
|  |  | Land tenure security improved | Implement the 4R waste management model — Reduce, Reuse, Recycle and Recover — in residential and commercial settings.
Establish and/or improve gazetted solid waste disposal sites in urban local governments.
Promote decent housing for the different income segments. |  |  |  | Develop and improve waste collection, transportation and disposal systems.
Promote waste segregation at source in residential, commercial and institutional areas.
Promote waste recovery, recycling and resource recovery facilities.
Strengthen capacity of Cities, Municipalities and urban Local Governments to manage solid waste.
Promote private-sector and community participation in waste management.
Monitor and enforce compliance with waste management standards and regulations.
Monitor implementation of waste management strategies and plans in Cities and Municipalities.
Increase economic opportunities in urban areas. |  |  |  | Rehabilitate and improve existing waste management facilities where required.
Strengthen the policy, legal, institutional, and coordination frameworks.

## Sheet2
Strategic Objective | Expected Result/outcome | Output | Key Activities/Actions (Quantified, location,period) | Cost UGX ,000 | Source of Funding
Strengthen and implement efficient land administration and management systems | Improved land Tenure Security Key Indicators 1. % Land surveyed 2. Turnround time (days) for titling; 3. % Land RegistereS | PIAP Output 06511101 NRECCLWM programme Policy frameworks developed/reviewed | Land related laws (Land Act, Land regulations and guidelines, RTA, Surveyors Act, Surveyor Registration Act) reviewed |  |  | 1
ADR guidelines on settling disputes on Customary land and other land tenures validated and disseminated in the 4 regions
Land related laws, policies, and guidelines disseminated in 50 District Local governments
40 Statutory Instruments for land acquisition drafted and issued
Revised National Land Policy,2025 disseminated
Land related laws, policies, and guidelines disseminated in 50 District Local governments
|  | Sub Total |  | 362100
|  | PIAP Output 06611101 Land Management and Valuation infrastructure enhanced | 500 Land Management institutions trained in land management
100 Land Management institutions supervised and inspected
50 DLBs vetted and approved
Membership dues to Uganda Law society and East African Law society paid
40 Land Dispute redress Committees in 40 Districts trained in ADR mechanisms
80 land transactions inspected for compliance with established legal and administrative standards
-Communities in Obongi and Rukiga mobilized and sensitized on SLAAC
22 MZOs in Central, Western, Northern and Eastern regions monitored and inspected.
-80 land transactions inspected for compliance with established legal and administrative standards.
Capacities of departmental staff enhanced in ADR in land management and best practices.
Local leaders and mediators in 40 Districts trained land dispute resolution.
Study on the effect of Certificates Of Occupancy on Mailo Land undertaken and report produced
Study undertaken on post issuance transactions for Certificates of Customary Ownerships and report produced
|  | Sub Total |  | 742000
Total-Land Administration |  |  |  | 1104000 | NWR
|  | PIAP Output 06611101 Land Management and Valuation infrastructure enhanced & PIAP Output 06611102 Land Surveys and registration programs implemented | -MLHUD IT Strategic Plan developed
Quarterly Uganda National Land Information System (UgNLIS) Performance reports produced and disseminated
MLHUD IT Strategic Plan developed
Microsoft 365 services for IT management services procured
-Redundant UgNLIS Links established in 10 MZOs
UgNLIS Security Operational Center (SOC) established and linked to the system across all MZOs
Customer Care service centre improved and upgraded to support the Public on Land Services
UgNLIS System upgrades tested and deployed in all MZOs
Routine maintenance of the MZOs IT infrastructure and UgNLIS system undertaken
Quarterly LAVMIS reports produced
20 staff trained and certified in IT courses i.e., ITIL/COBIT
MLHUD IT Risk management framework developed
UgNLIS Connectivity to Uganda Telecommunications Company Limited paid
Network Infrastructure upgraded to support UgNLIS service availability
Automatic Voltage Regulator procured to protect UgNLIS equipment
UgNLIS SMS alerts/ Notifications procured
22 MZOs monitored and provided with technical support
Performance review workshop for 60 IT staff (NLIC and MZOs) to strengthen capacity on merging technologies including blockchain and enhance delivery of ICT services conducted.
Production of 40,000 Titles supported
Processing of 20,000 Certificates of Customary Ownership (CCOs) supported.
|  | Sub Total |  | 8500000
Total land sector Reform |  |  |  | 8500000
|  | PIAP Output 06511101 NRECCLWM programme Policy frameworks developed/reviewed | -Registration of Titles Act amended
Trustees In cooperation Act ammended
|  | Sub Total |  | 220000
|  | PIAP Output 06611102 Land Surveys and registration programs implemented | -100,000 search letters issued from the Land Information System
1200 court case litigated for both male and female clients
300 public hearings conducted for all categories of clients including the elderly and Persons With Disability
Production of 40,000 Titles supported
Two multi-sectoral engagements undertaken on Improving Land Registration processes
Specialized Attire acquired for 10 Registrars of titles for attending court (flaps, gowns, shirts, file carrier bags)
40000 land titles issued to men, women and PWD's
Land registration activities in 22 MZOs monitored and supervised
80 Trustees registered
40 Land registrars from both Ministry Zonal Offices and Headquarters trained on best practices in land registration and continuous legal education with Uganda Law Society (ULS)
Subscription paid for renewal of practicing certificates for 20 Registrars
-31 land titles issued in fragile ecosystems (wetlands and forest reserves) investigated
2 Performance review workshops for Registrars of Titles undertaken
1 Project concept developed
Benchmarking visits on improving Land Management systems undertaken for 2 Department staff
|  | Subtotal |  | 878000
Total for land Registration |  |  |  | 1098000
PIAP Output 06511101 NRECCLWM programme Policy frameworks developed/reviewed
3 stakeholders engagements carried out on Survey and Mapping Bill, Survey Reports standards and National Mapping Standards developed.
| Sub total |  |  | 200000
|  | PIAP Output 06611102 Land Surveys and registration programs implemented | 500 copies of Maps for district and City Administrative Units printed and disseminated
100 copies of Tourist Map for Entebbe Municipality and Jinja City produced, printed and disseminated
Digitization and integration of large scale maps for 3 cities of Masaka, Soroti, Mbale and Masindi Municipality carried out
20kms Surveyed for Moroto Napak inter-district boundaries to reduce boundary disputes
6 International Boundary re-affirmation meetings held to reduce border disputes
54 Thematic maps revised for 6 districts (Nakaseke, Luwero, Nakasongola, Kiboga, Mityana & Kyankwanzi)
Restructuring of sixty (60) Mbarara ranches for automation of plot numbers and harmonization of five (5) overlapping blocks for Mukono & Kyadondo
20 Topographic Maps at the scale of 1:50,000 for Greater Kampala vectorized and updated
National Atlas revised
| Sub total |  |  | 1334700
Tota for Surveys and Mapping |  |  |  | 1534700
|  | PIAP Output 06611101 Land Management and Valuation infrastructure enhanced | Compensation rates for 135 districts reviewed
40 District Land Boards trained on the used of the Compensation rates database
Capacity of 15 Valuation Staff built in Valuation competencies
-80,000 property valuations carried out and supervised
Valuation activities Monitored in the 22 Ministry Zonal Offices
| sub total |  |  | 1173000
|  | valuation Project; PIAP Output 06611101 Land Management and Valuation infrastructure enhanced | 24 Handheld equipment (tablets) procured for rollout of Land Valuation Management Information System
Land Valuation Management Information System rolled out in 22 Ministry Zonal Offices
Property land value trend analysis conducted for 2 districts; Gulu and Jinja.
Land Valuation Management Information system and infrastructure maintained in all MZOs
Refresher trainings on navigation of LAVMIS undertaken for 40 Valuers at Headquarters and the Ministry Zonal Offices
-02 Regional Stakeholder engagements undertaken for external users of LAVMIS in Western and Northern regions
Valuation Act 2025 gazetted
500 copies of the Valuation Act 2025 produced
Valuation Regulations developed
Financial support 200m provided for the establishment of the Institute of Certified Valuers
Countrywide market research on land values undertaken
Improve intergrated land use planning, implementation and development systems in rural and urban areas | Orderly Development | %level of compliance to landuse frameworks |  |  |  | 1. Physical Planning; 2. Land Use Regulation, Compliance and Enforcement; 3. MZOs; 4. UCMID
Develop livable, productive, inclusive, environmentally resilient urban systems | Orderly Development | %level of compliance to landuse frameworks
Develop and implement housing dwliveery programs and real estate bmarket systems | Increased housing stock | %reduction in housing deficit |  |  |  | 1. Human settlements; 2. Housing and Real Estate Management
Strengthen policy, legal, institutional and coordination frameworks | Harmonised planning and implementation frameworks | % increase in performance of the Ministry | 22 MZO vehicles serviced and maintained |  |  | 1. Finance and Administration; 2.Statistics, Research, Monitroring and Evaluation 3. LECP