MINISTRY OF LANDS, HOUSING AND URBAN DEVELOPMENT

QUARTER ONE PERFORMANCE REPORT FOR FY 2026/2027

Department: MINISTRY ZONAL OFFICES

| KEY SERVICE AREA/PIAP output | Annual Output | Planned Q1 Target | Approved budget | Warrants |  | Achieved Q1 physical performance | Amount Spent | Reasons for Variation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Key Service Area: 000039 Policies, Regulations and Standards; PIAP Output 10511201 Policy and Legal Framework developed, reviewed, and implemented (PAS) | 04 Barazas organized at the MZOs on land management issues. and to sensitize the public on Ministry services | 01 Baraza organized at the MZOs on land management issues. and to sensitize the public on Ministry services | 12,821,612 | 3,591,200 |  | Attended the 5th Land Camp from 19th to 20th August 2026 in Apac District, Attended Finance Committee Meeting on the 13th July 2026 and BlockChain & AI digital Land Registry & Managemt on the 16th July 2026 at MLHUD the Headquaters. | 3,591,200 | Partial funds released since the 5th Land Camp in Apac District was co-sponsored by the Eastern and Southern Africa Small Scale Farmers Forum(ESAFF) Uganda. |
|  | 04 Locus visits and boundary opening undertaken within the MZOs’ jurisdictions | 01 Locus visit and boundary opening undertaken within the MZOs’ jurisdictions | 7,692,967 | 8,566,400 |  | Travel inland funds facilitated transportation of 04 Book Shelves on the 03rd July 2026, 09 Office Chairs on the 08th July 2026, 6th Administrative meeting in Gulu from 07th-11th Sept. 2026, attend Budget Meeting to review & rationalise the 2026/2027 Budget at the H/Qs, deliver Lira MZO Workplan & Budget on the 17th August 2026. | 8,566,400 | Inadequate allocation since a number of activities got facilitated from the Travel Inland Budget. |
|  | Capacity building of 08 MZO staff undertaken in various fields. | Capacity building of 02 MZO staff undertaken in various fields. | 3,077,186 | 3,077,186 |  | 18 Staff trained on filling Performance Appraisal Reports. | 3,077,186 | Achieved. Lira MZO Staff members trained on filling Performance Appraisal & code of conduct for Public Officers . |
|  | 04 Annual subscriptions made to professional bodies | 01 Annual subscription made to a professional body | 0 | 0 |  | Nil | 0 | Allocation not warranted and requisation not submitted for approvals . |
|  | Minor civil repairs of the MZO structures undertaken | 01 office block painted (administration block) | 11,283,019 | 8,617,000 |  | Drainage works to open up blocked sewage line & Electrical Maintenance conducted at Lira MZO. | 8,617,000 | Partial request made due to unresolved issues in respect to topping up consolidated allowances for the eligible staff . |
|  | Annual Revenue Generated within the MZO's jurisdiction | Q1 revenue of UGX 473,000,000 collected |  |  |  |  |  |  |
|  | 04 radio talk shows held on Land Management | 01 radio talk show held on Land Management | 4,102,916 | 0 |  | Nil | 0 | Not achieved. No funds released to Lira MZO for advertising and public relations due to wrong code used for charging the expenditure line(221012) instead of 221001. It shall be rectified and resubmitted. |
|  | National Land Valuation Management Information System (N-LaVMIS) managed | 01 Training session and rolling out of N-LaVMIS undertaken | 0 | 0 |  | NA | 0 | NA |
|  | 04 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken | 01 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken | 0 | 0 |  | NA | 0 | NA |
|  | 12 Court cases litigated | 03 Court cases litigated | 0 | 0 |  | NA | 0 | NA |
|  | 20,000 titles produced and issued, including SLAAC | 5,000 titles produced and issued, including SLAAC | 0 | 0 |  | NA | 0 | NA |
|  | 60,000 SLAAC titles produced and issued | 15,000 SLAAC titles produced and issued | 0 | 0 |  | 4,178 SLAAC Titles dispatched to Apac (3,830) & Oyam (348) | 0 | Data Processing Centre to speed up processing of SLAAC Titles. |
|  | 20,000 Certificates of Customary Ownership titles processed and issued. | 5,000 Certificates of Customary Ownership titles processed and issued. | 0 | 0 |  | 261 Certificate of Customary Ownership(C.C.Os) printed & dispatched for CORDAID & 111 C.C.Os printed & dispatched to VNG. | 0 | Deskwork but stationery and tonner should be provided if possible. |
|  | MZO equipment serviced and maintained, including computers, printers and scanners | MZO office equipment (computers) serviced | 0 | 0 |  | NA | 0 | NA |
|  | MZO Vehicles serviced and maintained | 01 MZO Vehicle serviced and maintained | 5,128,645 | 5,128,645 |  | 01 vehicle (UG 30 000 72) assessed by Ministry of Works at their Regional UNRA Office in Lira & repaired by Jokis Eng- Service Limited based in Lira City & Shell Lira. | 5,128,645 | Achieved |
|  | Staff team-building, health and wellness activities conducted | 01 staff team-building and wellness sessions conducted | 0 | 0 |  | NA | 0 | NA |
|  | Gender, HIV/AIDS, environment and other crosscutting issues mainstreamed | 100 condoms supplied to staff 02 awareness activities conducted | 0 | 0 |  | NA | 0 | NA |
|  | 01 Land awareness week conducted | 01 Stakeholder engagements conducted | 0 | 0 |  | NA | 0 | NA |
|  | Finance Committee Meetings facilitated | 01 Finance Committee Meetings facilitated | 0 | 0 |  | Finance Committee Meeting organised by the Headquaters and attended by MZO Heads. | 0 | NA |
|  | 04 batches of Consolidated Staff Allowances provided Quaterly to Lira MZO Staff | 01 Consolidated Staff Allowances provided for Q1 | 4,102,916 | 9,294,000 |  | 06 members of Lira MZO Staff benefited. | 9,294,000 | 02 Permanent Staff missed out worth UGX 2,700,000. ( Registrar Namukali Bob & Dispatch Clerk Umar Malongo) |
|  | 04 Quaterly Provision for Welfare & Entertainment made. | 1 Quaterly Provision for Welfare & Entertainment ma | 0 | 2,000,000 |  | 01 water dispenser, water, sugar, biscuits, sugar and tea bags procured. | 2,000,000 | Achieved |
|  | 04 Quaterly Provision for Small Office Equipments made. | 01 Quaterly Provision for Small Office Equipments made. | 0 | 283,018 |  | DSTV LNB replaced at Lira MZO for clear signal | 283,000 | Achieved |
|  | 04 Quaterly releases for Fuel, Lubricants & Oils | 01 Quaterly release for Fuel, Lubricants & Oils | 8,205,832 | 8,205,832 |  | Both Generator & Vehicle fuel released for operations | 8,205,832 | Achieved |
|  | Sub-Total |  | 56,415,094 | 48,763,263 |  |  | 48,763,263 |  |
|  | Total |  |  |  |  |  |  |  |

Name:										Signature:					Date:

Head of Department/Project Coordinator/MZO Head

Attach signed departmental minutes