MINISTRY OF LANDS, HOUSING AND URBAN DEVELOPMENT

QUARTER ONE PERFORMANCE REPORT FOR FY 2026/2027

Department: MINISTRY ZONAL OFFICES (SOROTI)

| KEY SERVICE AREA/PIAP output | Annual Output | Planned Q1 Target | Approved budget | Warrants |  | Achieved Q1 physical performance | Amount Spent | Reasons for Variation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Key Service Area: 000039 Policies, Regulations and Standards; PIAP Output 10511201 Policy and Legal Framework developed, reviewed, and implemented (PAS) | 04 Barazas organized at the MZOs on land management issues. and to sensitize the public on Ministry services | 01 Baraza organized at the MZOs on land management issues. and to sensitize the public on Ministry services | 4,102,916 | 4,102,916 |  | One Barraza organized at MZO but not yet implemented | 4,102,916 | 4,102,916 to be implemented in quarter two. |
|  | 04 Locus visits and boundary opening undertaken within the MZOs’ jurisdictions | 01 Locus visit and boundary opening undertaken within the MZOs’ jurisdictions | 7,692,967 | 7,692,967 |  | Locus visits done and completed at Katakwi. Carried out inspection of surveys at Iriri cattle quarantine. Carried out inspection and verification of surveys at Tisai Kumi. Carried out inspection and verification of survey overlap at Ochuloi rock Soroti. | 7,692,967 |  |
|  | Capacity building of 08 MZO staff undertaken in various fields. | Capacity building of 02 MZO staff undertaken in various fields. | 12,821,612 | Nil |  | Nil | Nil | Funds not approved |
|  | 04 Annual subscriptions made to professional bodies | 01 Annual subscription made to a professional body |  |  |  |  |  | 0 |
|  | Minor civil repairs of the MZO structures undertaken | 01 office block painted (administration block) | 10,000,000 | 10,000,000 |  | Renovations and repairs completed at Soroti MZO (broken and leaking gutters, Tanks washed, leaking eaves and verandas repaired, Faulty electrical installations corrected. Blown bulbs replaced. Broken doors and locks repaired and replaced, broken toilets repaired.) | 10,000,000 | Nil |
|  | Annual Revenue Generated within the MZO's jurisdiction | Q1 revenue of UGX 473,000,000 collected |  |  |  |  |  |  |
|  | 04 radio talk shows held on Land Management | 01 radio talk show held on Land Management | 5,593,122 | Nil |  | Nil | Nil | Not funded |
|  | National Land Valuation Management Information System (N-LaVMIS) managed | 01 Training session and rolling out of N-LaVMIS undertaken |  | 0 |  |  | 0 | 0 |
|  | 04 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken | 01 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken | 0 | 0 |  |  | 0 | 0 |
|  | 12 Court cases litigated | 03 Court cases litigated | 0 | 0 |  |  | 0 | 0 |
|  | 1500 titles to be produce and issue | 500 titles produced and issued |  |  |  |  | 0 | 0 |
|  | MZO equipment serviced and maintained, including computers, printers and scanners | MZO office equipment (computers) serviced | 0 |  |  |  | 0 | 0 |
|  | MZO Vehicles serviced and maintained | 02 MZO Vehicles serviced and maintained | 5,128,645 | 5,128,000 |  | Vehicle serviced and repaired (fixing clutch plates replaced, leakages in the oil and fuel repaired, faulty wiring and lights repaired.) | 5,128,000 | Nil |
|  | Staff team-building, health and wellness activities conducted | 01 staff team-building and wellness sessions conducted |  | 0 |  | Funds not release | 0 | 0 |
|  | Gender, HIV/AIDS, environment and other crosscutting issues mainstreamed | 100 condoms supplied to staff 02 awareness activities conducted |  | 0 |  | Funds not release | 0 | 0 |
|  | 01 Land awareness week conducted | 05 Stakeholder engagements conducted |  | 0 |  |  | 0 | 0 |
|  | Finance Committee Meetings facilitated | 01 Finance Committee Meetings facilitated |  | 0 |  |  |  |  |
|  | Fuel, oil ,luburants | One vehicle and generator fuel, | 8,205,832 | 8205,832 |  | Fuel oil and lubricants purchased for vehicle and generator. | 8,205,823 | Nil |
|  | Sub-Total | Approved budget | 73,000,000 | 53,000,000 |  |  |  |  |
|  |  | Deficit |  | 18,414,734 |  | Requisitions not honored |  |  |
|  | Total |  |  | 34,585,266 |  | Amount received | 30,482,350 |  |

Name:	 Edison Atwau 	Signature:					Date:

Head of Department/Project Coordinator/MZO Head

Challenges Faced;

- Staffing Constraints: Most of the personnel running operations at the MZOs are on short-term contracts.

- Transport Logistics Bottleneck: The entire MZO relies on a single (01) vehicle for all field activities and yet the activities of the MZO are field based.

- Delays Release of Funds: The funds were released towards the closed of the first quarter, making implementation difficult.

- The Revenue collected could not be established as the system is switched off

- Land Titling Verification Failure: The titles could not be verified because the system is switched off.

Cross-Cutting Issues (Quarter One)

- Workplace Health and Wellness Mainstreaming:  activity not done due to none release of funds.

PRARIORITIES FOR QUARTER TWO

N-LaVMIS System Rollout: Initiate training sessions and begin the phased field deployment of the National Land Valuation Management Information System (N-LaVMIS

- Mass Media Outreach: Hold the postponed radio talk shows on Land Management to educate the public on land rights.

- Land Awareness Campaigns: Conduct the deferred Land Awareness Week and facilitate the 05 planned stakeholder engagements.

- Health and Wellness Interventions: Resume workplace health interventions, including the supply of 100 condoms to staff and conducting the 02 deferred awareness activities.

- Staff Welfare:

- Capacity building for staff:

- Backstopping to the land boards and physical planning

- Travel inland for all the staff to attend mandatory meetings

- Distribution of the SLAAC Titles.

- Mediations on disputed issues regarding land

- Litigation

- Gender, HIV/AIDS, environment and other crosscutting issues mainstreamed

- Purchase of tyres for the vehicle

- Re construction of the old of perimeter wall for the MZO

Attach signed departmental minutes