MINISTRY OF LANDS, HOUSING AND URBAN DEVELOPMENT

QUARTER ONE PERFORMANCE REPORT FOR FY 2026/2027

Department: MINISTRY ZONAL OFFICES

| KEY SERVICE AREA/PIAP output | Annual Output | Planned Q1 Target | Approved budget | Warrants |  | Achieved Q1 physical performance | Amount Spent | Reasons for Variation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Key Service Area: 000039 Policies, Regulations and Standards; PIAP Output 10511201 Policy and Legal Framework developed, reviewed, and implemented (PAS) | 04 Barazas organized at the MZOs on land management issues. and to sensitize the public on Ministry services | 01 Baraza organized at the MZOs on land management issues. and to sensitize the public on Ministry services |  |  |  | N/A | … | Planned for 2nd and 4th quarters |
|  | 04 Locus visits and boundary opening undertaken within the MZOs’ jurisdictions | 01 Locus visit and boundary opening undertaken within the MZOs’ jurisdictions |  |  |  | No activity done this quarter |  | Equipment came toward the end of quarter 1 |
|  | Capacity building of 08 MZO staff undertaken in various fields. | Capacity building of 02 MZO staff undertaken in various fields. |  |  |  | Not planned but very important |  |  |
|  | 04 Annual subscriptions made to professional bodies | 01 Annual subscription made to a professional body |  |  |  | Not planned for |  |  |
|  | Minor civil repairs of the MZO structures undertaken | 01 office block painted (administration block) | 22,500,000 |  |  | Electricity services, Plumbing work done, replaced sceptic tank Covers, sock pit dug and built, office entry repaired etc | 8,783,019 |  |
|  | Annual Revenue Generated within the MZO's jurisdiction | Q1 revenue of UGX 473,000,000 collected |  |  |  |  |  |  |
|  | 04 radio talk shows held on Land Management | 01 radio talk show held on Land Management | 8,181,818 |  |  | two radio talk shows held. | 4,102,916 |  |
|  | National Land Valuation Management Information System (N-LaVMIS) managed | 01 Training session and rolling out of N-LaVMIS undertaken |  |  |  | N/A |  |  |
|  | 04 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken | 01 out-of-court Mediation and Alternative Dispute Resolution (ADR) activities undertaken |  |  |  | Continued with ADR |  | Used office impress |
|  | 12 Court cases litigated | 03 Court cases litigated |  |  |  | Continued with cases in court |  | Use office impress |
|  | 20,000 titles produced and issued, including SLAAC | 5,000 titles produced and issued, including SLAAC |  |  |  | N/A |  | No SLAAC program at the MZO as yet |
|  | MZO equipment serviced and maintained, including computers, printers and scanners | MZO office equipment (computers) serviced |  |  |  | Computers, Printers and AC all serviced | 2,500,000 |  |
|  | MZO Vehicles serviced and maintained | 02 MZO Vehicles serviced and maintained | 10,227,094 |  |  | Motor vehicle services and minor repairs done | 5,128,645 |  |
|  | Staff team-building, health and wellness activities conducted | 01 staff team-building and wellness sessions conducted | 6,136,364 |  |  | Public address system procured for wellness program and other programs. Wellness trainer paid. | 3,077,187 |  |
|  | Gender, HIV/AIDS, environment and other crosscutting issues mainstreamed | 100 condoms supplied to staff 02 awareness activities conducted |  |  |  | N/A |  | Not planned but necessary |
|  | 01 Land awareness week conducted | 05 Stakeholder engagements conducted |  |  |  | N/A |  | Planned for Quarter 2 and 4 |
|  | Finance Committee Meetings facilitated | 01 Finance Committee Meetings facilitated |  |  |  | Two meetings held | 2,500,000 | Committee meeting facilitated with refreshment - this is also the vote being used for office impress. |
|  | Sub-Total |  | 73,000,000 | 53,000,000 |  |  | …….. |  |
|  | Total |  |  |  |  |  |  |  |

Name:		Philip Adonga		Signature:						Date:

Head of Department/Project Coordinator/MZO Head

Attach signed departmental minutes